## Table 1
भारत सरकार Government of India विद्युत मंत्रालय Ministry of Power के न्द्री य वि द्यु त प्रा विक र ण Central Electricity Authority
निीकरणीय पररयोजना प्रबोिन प्रभाग
Renewable Project Monitoring Division
March-2026 / मार्च-2026
Preface India has successfully achieved 223.27 GW of RE Installed capacity (excluding Large Hydro) by the end of March 2026 and a significant number of Renewable Energy (RE) projects are under various stages of construction. As on 31 March, 2026, a total RE Capacity of 138320.685 MW is under-construction which comprises of 90039.9 MW of Solar Projects, 29281.9 MW of Wind projects, 18998.885 MW of Hybrid projects.
This report mostly contains information of Solar Projects which have capacity equal to 25 MW or above. Also it does not contain information of the Rooftop Grid connected and off Grid Solar Power Projects.
This Report highlights the progress of active under-construction RE projects (excluding Large Hydro) of SECI, CPSUs under MoP (NTPC, NHDC, SJVNL, NHPC, THDC), various States (Andhra Pradesh, Assam, Bihar, Chhattisgarh, Delhi, Gujarat, Jharkhand Himachal Pradesh, Karnataka, Kerala, Maharashtra, Madhya Pradesh, Uttar Pradesh, Odisha Rajasthan, Tamil Nadu) and development of Projects in Solar Parks/UMREPP (Ultra Mega Renewable Energy Power projects). The information available on the E-gen portal of CEA, has also been appropriately incorporated in addition to the above details reported by the various entities.
Summary of location based State-wise Under-construction RE Projects in the country (in MW)
Name of State | Hybrid | Solar | Wind | Total
Andhra Pradesh | 3187 | 3500 | 1949.8 | 8636.8
Assam | - | 400 | - | 400
Chhattisgarh | - | 26 | - | 26
Gujarat | 6991 | 19640 | 5793 | 32424
Himachal Pradesh | - | 360 | - | 360
Jharkhand | - | 353 | - | 353
Karnataka | 2589.08 | 4754.6 | 9991.9 | 17335.58
Kerala | 100 | 100 | - | 200
Madhya Pradesh | 1664.8 | 2185 | 2802 | 6651.8
Maharashtra | 1752 | 3243.8 | 4301 | 9296.8
Odisha | - | 60 | - | 60
Punjab | - | 15 | - | 15
Rajasthan | 2565 | 40229.5 | 3320.7 | 46115.2
Tamil Nadu | - | 200 | 973.5 | 1173.5
Telangana | - | 176 | - | 176
Uttar Pradesh | - | 3770 | - | 3770
West Bengal | - | 419 | - | 419
Location yet to be decided | 150 | 10608 | 150 | 10908
Grand Total | 18998.88 | 90039.9 | 29281.9 | 138320.68
वनमााणािीन निीकरणीय ऊजाा पररयोजना वतमाही ररपोर्ा
Quarterly Report on Under-construction Renewable Energy Projects

## Table 2
Summary of Under-Construction RE Projects of CPSUs under MoP (in MW)
S. No. | Name of CPSUs | Solar | Wind | Hybrid | Total
1 | NTPC | 9962 | 2971 | 454 | 13087
2 | SJVN | 2043 | 700 | 0 | 2043
3 | NHPC | 1460 | 0 | 0 | 1460
4 | DVC | 596 | 50 | 0 | 646
| Total | 14061 | 3721 | 454 | 17236

## Table 3
Summary of under construction Projects of CPSUs under Ministry of Power
Sl. No. | Name of the Project | Name of the Developer | Project Location | Under Construction Capacity (MW) | Expected date of completion | Type of Project (Solar/Wind/ Hybrid )
NTPC
1 | Ramagundam | NTPC Ltd | State-Telangana | 176 | 2026-04-30 | Ground & Floating Solar
2 | Sipat | NTPC Ltd | State-Chhattishgarh | 26 | 2026-07-31 | Solar PV Project Floating
3 | Vidhyanchal | NTPC Ltd | Madhya Pradesh | 20 | 2026-12-08 | Solar PV Project Ground Mounted
4 | Rihand Solar | NTPC Ltd | State- Uttar Pradesh | 20 | 2026-04-30 | Solar PV Project Ground Mounted
5 | GUVNL-I, Kankachiyala, Rupakheda & Sadla | NTPC REL | State- Gujarat (3 locations) | 137 | 2026-06-30 | Solar PV Project Ground Mounted
6 | Bhuj Solar 300MW Nakhatrana & Part of hybrid: Dayapar-I - WIND 150MW | NTPC REL | State- Gujarat | 304 | 2026-12-31 | Hybrid Projecet
7 | Khavda Ph II | NTPC REL | State- Gujarat | 195 | 2026-05-31 | Solar PV Project Ground Mounted
8 | DAYAPAR-II Wind | NTPC REL | State- Gujarat | 150 | 2027-03-31 | Wind
9 | Jamjodhpur, Jamnagar | NTPC REL | State- Gujarat | 630 | 2027-01-31 | Wind
10 | Vanki, Kachchh | NTPC REL | State- Gujarat | 180 | 2026-08-31 | Wind
11 | Kalasar-I, Bikaner-II | NTPC REL | State-Rajasthan | 250 | 2026-06-30 | Solar PV Project Ground Mounted
12 | Kalasar-II, Bikaner-II, | NTPC REL | State-Rajasthan | 250 | 2026-06-30 | Solar PV Project Ground Mounted
13 | Gadag (Taralakatti & Halligudi) | NTPC REL | State-Karnataka | 378 | 2027-03-31 | Wind
14 | GSECL Khavda Ph V | NTPC REL | State- Gujarat | 200 | 2027-01-31 | Solar PV Project Ground Mounted
15 | GSEC Khavda VI | NTPC REL | State- Gujrat | 225 | 2026-06-30 | Solar PV Project Ground Mounted
16 | Khavda IX | NTPC REL | State- Gujarat | 245 | 2027-03-31 | Solar PV Project Ground Mounted
17 | Khavda VII | NTPC REL | State- Gujarat | 275 | 2026-06-30 | Solar PV Project Ground Mounted
18 | Khavda VIII | NTPC REL | State- Gujarat | 275 | 2026-08-31 | Solar PV Project Ground Mounted
19 | Bikaner I Block-1 | NTPC REL | State-Rajasthan | 325 | 2027-03-31 | Solar PV Project Ground Mounted
20 | Bikaner I Block-2 | NTPC REL | State-Rajasthan | 325 | 2027-03-31 | Solar PV Project Ground Mounted
21 | Maharashtra wind | NTPC REL | Maharashtra | 739 | 2027-12-31 | Wind
22 | Bellary, KA-V | NTPC REL | State-Karnataka | 894 | 2027-12-31 | Wind
23 | Khavda-IV | NTPC REL | State- Gujarat | 1200 | 2027-03-31 | Solar PV Project Ground Mounted
24 | Khavda-III Solar (300 MW) ) & Part of Hybrid: Dayapar-III 150MW Wind | NTPC REL | State- Gujarat | 150 | 2027-03-31 | Hybrid Projecet
25 | Chitrakoot-I | NTPC REL | Uttar Pradesh | 400 | 2027-03-31 | Solar PV Project Ground Mounted
26 | Fatehgarh-I | NTPC REL | Rajashan | 300 | 2027-03-31 | Solar PV Project Ground Mounted
27 | Barethi Solar Park | NTPC Renewable Energy Ltd. | Barethi , Madhya Pradesh | 0 | 2027-12-31 | Solar
28 | NTPC REL. Khavda 4750 MW Solar Park | NTPC Renewable Energy Ltd. | Khavda, Bhuj, Gujarat | 3418 | 2027-12-31 | solar
29 | Lalitpur Solar Project/TUSCO Ltd. (JV of THDCIL & UPNEDA) | M/s NTPC Renewables Energy Ltd. (SPD) | Tehsil Talbehat, Dist. Lalitpur, (U.P.) | 600 | 2027-06-03 | Solar
30 | Chitrakoot Solar Project/TUSCO Ltd. (JV of THDCIL & UPNEDA) | M/s NTPC Renewables Energy Ltd. (SPD) | Tehsil Mau, Dist. Chitrakoot, (U.P.) | 800 | 2027-06-03 | Solar
TOTAL; |  |  |  | 13087
SJVN
1 | GUVNL Phase –XVII (Khavda SPP) | SJVN GREEN ENERGY LIMITED | Gujarat | 50 | 2026-07-31 | Solar
2 | 50 MW Gujrai Solar Power Station, SJVN Green Energy Limited | SJVN Green Energy Limited | Vill-Gujrai Tehsil-Akbarpur Dist-Kanpur Dehat, Uttar Pradesh | 150 | 2027-05-31 | Solar
3 | 100MW Raghanesda Solar Power Project SJVN Green Energy Limited | SJVN Green Energy Limited | Plot-C, Vill-Raghnesda Tehsil-Vav. Dist-Banaskantha, Gujarat | 150 | 2027-04-30 | Solar
4 | Gujarat Urja Vikas Nigam Ltd. (GUVNL) Solar Phase XI, Bagodara SPP | SJVN GREEN ENERGY LIMITED | Surendranager , Gujarat | 100 | 2026-09-30 | Solar
5 | Dhubri SPP (APDCL) | SJVN GREEN ENERGY LIMITED | Assam | 100 | 2026-03-31 | Solar
6 | BBMB 18 MW | SJVN GREEN ENERGY LIMITED | Punjab,Himac hal | 100 | 2026-09-30 | Solar
7 | BBMB 15 MW | SJVN GREEN ENERGY LIMITED | Himachal Pradesh | 260 | 2026-12-31 | Solar
8 | GUVNL Solar Phase -XIV | SJVN GREEN ENERGY LIMITED | Gujarat | 200 | 2026-03-31 | Solar
9 | 200 MW Khavda SJVN Solar Power Project Phase 23 | SJVN Limited | Gujarat,Khavd a RE park | 200 | 2026-11-20 | Solar groundmlounted project
10 | CPSU SCHEME PHASE –II, Tranche -III | SJVN GREEN ENERGY LIMITED | Rajasthan | 18 | 2026-08-30 | Solar
11 | Punjab State Power Corporation Ltd. (PSPCL) ET-2 | SJVN GREEN ENERGY LIMITED | Punjab | 15 | 2027-12-31 | Solar

## Table 4
12 | Sonitpur SPP (APDCL) | SJVN GREEN ENERGY LIMITED | Assam | 300 | 2027-04-30 | Solar
13 | Rajasthan Urja Vikas Nigam Ltd. (RUVNL) SPP, Nawa | SJVN GREEN ENERGY LIMITED | Rajasthan | 400 | 2027-01-31 | Solar
14 | 690 MW ISTS-connected Wind Power Projects (Tranche-XIV) | SJVN Green Energy Ltd | Madhya Pradesh | 700 | 2027-03-31 | Wind
TOTAL; |  |  |  | 2743
NHPC
1 | NHPC Limited | NHPC Limited | NP Kunta, Andhra Pradesh | 100 | 2026-06-30 | Solar
2 | NHPC Limited | NHPC Limited | Ladeihil,Jagan ath Prasad,Ganja m , Odisha | 40 | 2026-06-30 | Solar
3 | NHPC Limited | NHPC Limited | Khavda,Bhuj,K utch Gujarat | 600 | 2026-12-19 | Solar
4 | NHPC Limited | NHPC Limited | West Kallad, Kollam , Kerala | 50 | 2026-12-31 | Floating Solar
5 | NHPC Limited | NHPC Limited | Khavda,Bhuj,K utch Gujarat | 200 | 2026-06-30 | Solar
6 | NHPC Limited | NHPC Limited | Khavda,Bhuj,K utch Gujarat | 200 | 2026-04-30 | Solar
7 | Mirzapur Solar Park | Bundelkhand Saur Urja Limited – BSUL – a JV of NHPC & UPNEDA | Sherwa, District Mirzapur, Uttar Pradesh | 200 | 2026-12-31 | Solar
8 | Floating Solar Park | NHPC Limited | West Kallada, Kerala | 50 | 2027-12-31 | solar
9 | Odisha Solar Park | NHPC Limited | Landehill, Ganjam, Odisha | 20 | 2026-12-31 | Solar
TOTAL; |  |  |  | 1460
DVC
1 | Damodar Valley Corporation (DVC) | SPD | Konar, JH | 8 | 2026-12-31 | Solar (Ground Mounted)
2 | Jam Khambalia [DVC] | Avaada GJClean Pvt Ltd | Jam Khambalia, Gujarat | 50 | 2026-05-31 | Wind
3 | Damodar Valley Corporation (DVC) | SPD | RTPS, WB | 10 | 2026-12-31 | Solar (Floating Solar on Raw Water Reservoir of TPP)
4 | Damodar Valley Corporation (DVC) | SPD | MTPS, WB | 14 | 2026-12-31 | Solar (Floating Solar on Raw Water Reservoir of TPP)
5 | DVC Floating Solar Park Ph-I | Green Valley Renewable Energy GVREL - A JV of DVC & NTPC Green Energy Limited | Tilaya Dam, Koderma, Jharkhand And, Panchet Dam, Dhanbad, Jharkhand (part of project in West Bengal) | 310 | 2027-12-31 | Solar
6 | DVC Floating Solar Park Ph-II | Green Valley Renewable Energy GVREL - A JV of DVC & NTPC Green Energy Limited | Maithon Dam, Dhanbad, Jharkhand (part of project in West Bengal) | 234 | 2027-12-31 | Solar
7 | Damodar Valley Corporation (DVC) | SPD | CTPS, Jharkhand | 10 | 2026-12-31 | Solar
8 | Damodar Valley Corporation (DVC) | SPD | Rooftop PV Plant at different location of DVC at Jharkand and West Bengal | 10 | 2026-12-31 | Solar
TOTAL; |  |  |  | 646

## Table 5
Under-construction Renewable Energy Capacity All across the Country including CPSUs under MoP and SECI under MNRE (in MW).
S. No. | Name of the Project | Name of the Developer | Project location (Village/ | Project Capacity for | Project Capacity | Under Construction | Date of completion |  | Type of Project (Solar/ Wind/ Hybrid )
| District/ State) |  |  | execution (MW) | Commissio ned (MW) | Capacity (MW) | Scheduled | Anticipated
1 | Ramagundam | NTPC Ltd | State- Telangana | 176 | 0 | 176 | 2025-09-30 | 2026-04-30 | Ground & Floating Solar
2 | Sipat | NTPC Ltd | State-Chhattishgarh | 26 | 0 | 26 | 2025-03-31 | 2026-07-31 | Solar PV Project Floating
3 | Vidhyanchal | NTPC Ltd | Madhya Pradesh | 20 | 0 | 20 | 2026-12-08 | 2026-12-08 | Solar PV Project Ground Mounted
4 | Rihand Solar | NTPC Ltd | State- Uttar Pradesh | 20 | 0 | 20 | 2025-02-28 | 2026-04-30 | Solar PV Project Ground Mounted
5 | GUVNL-I, Kankachiyala, Rupakheda & Sadla | NTPC REL | State- Gujarat (3 locations) | 200 | 63 | 137 | 2022-07-31 | 2026-06-30 | Solar PV Project Ground Mounted
6 | Bhuj Solar 300MW Nakhatrana & Part of hybrid: Dayapar-I - WIND 150MW | NTPC REL | State- Gujarat | 450 | 146 | 304 | 2023-11-30 | 2026-12-31 | Hybrid Projecet
7 | Khavda Ph II | NTPC REL | State- Gujarat | 1200 | 1005 | 195 | 2024-12-31 | 2026-05-31 | Solar PV Project Ground Mounted
8 | DAYAPAR-II Wind | NTPC REL | State- Gujarat | 200 | 50 | 150 | 2026-01-31 | 2027-03-31 | Wind
9 | Jamjodhpur, Jamnagar | NTPC REL | State- Gujarat | 630 | 0 | 630 | 2025-05-31 | 2027-01-31 | Wind
10 | Vanki, Kachchh | NTPC REL | State- Gujarat | 180 | 0 | 180 | 2025-06-30 | 2026-08-31 | Wind
11 | Kalasar-I, Bikaner-II | NTPC REL | State- Rajasthan | 250 | 0 | 250 | 2026-03-31 | 2026-06-30 | Solar PV Project Ground Mounted
12 | Kalasar-II, Bikaner-II, | NTPC REL | State- Rajasthan | 250 | 0 | 250 | 2026-03-31 | 2026-06-30 | Solar PV Project Ground Mounted
13 | Gadag (Taralakatti & Halligudi) | NTPC REL | State- Karnataka | 378 | 0 | 378 | 31-06-2026 | 2027-03-31 | Wind
14 | GSECL Khavda Ph V | NTPC REL | State- Gujarat | 200 | 0 | 200 | 2025-10-31 | 2027-01-31 | Solar PV Project Ground Mounted
15 | GSEC Khavda VI | NTPC REL | State- Gujrat | 225 | 0 | 225 | 2026-03-31 | 2026-06-30 | Solar PV Project Ground Mounted
16 | Khavda IX | NTPC REL | State- Gujarat | 245 | 0 | 245 | 2026-04-30 | 2027-03-31 | Solar PV Project Ground Mounted
17 | Khavda VII | NTPC REL | State- Gujarat | 275 | 0 | 275 | 2026-03-31 | 2026-06-30 | Solar PV Project Ground Mounted
18 | Khavda VIII | NTPC REL | State- Gujarat | 275 | 0 | 275 | 2026-03-31 | 2026-08-31 | Solar PV Project Ground Mounted
19 | Bikaner I Block-1 | NTPC REL | State- Rajasthan | 325 | 0 | 325 | 2026-10-31 | 2027-03-31 | Solar PV Project Ground Mounted
20 | Bikaner I Block-2 | NTPC REL | State- Rajasthan | 325 | 0 | 325 | 2026-10-31 | 2027-03-31 | Solar PV Project Ground Mounted
21 | Maharashtra wind | NTPC REL | Maharashtra | 739 | 0 | 739 | 2027-12-31 | 2027-12-31 | Wind
22 | Bellary, KA-V | NTPC REL | State- Karnataka | 894 | 0 | 894 | 2027-12-31 | 2027-12-31 | Wind
23 | Khavda-IV | NTPC REL | State- Gujarat | 1200 | 0 | 1200 | 2026-01-12 | 2027-03-31 | Solar PV Project Ground Mounted
24 | Khavda-III Solar (300 MW) ) & Part of Hybrid: Dayapar-III 150MW Wind | NTPC REL | State- Gujarat | 450 | 300 | 150 | 2025-05-31 | 2027-03-31 | Hybrid Projecet
25 | Chitrakoot-I | NTPC REL | Uttar Pradesh | 400 | 0 | 400 | 2025-11-23 | 2027-03-31 | Solar PV Project Ground Mounted
26 | Fatehgarh-I | NTPC REL | Rajashan | 300 | 0 | 300 | 2027-05-18 | 2027-03-31 | Solar PV Project Ground Mounted
27 | Barethi Solar Park | NTPC Renewable Energy Ltd. | Barethi , Madhya Pradesh | 630 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
28 | NTPC REL. Khavda 4750 MW Solar Park | NTPC Renewable Energy Ltd. | Khavda, Bhuj, Gujarat | 4750 | 1332 | 3418 | 2027-12-31 | 2027-12-31 | solar
29 | Lalitpur Solar Project/TUSCO Ltd. (JV of THDCIL & UPNEDA) | M/s NTPC Renewables Energy Ltd. (SPD) | Tehsil Talbehat, Dist. Lalitpur, (U.P.) | 600 | 0 | 600 | 2027-06-03 | 2027-06-03 | Solar
30 | Chitrakoot Solar Project/TUSCO Ltd. (JV of THDCIL & UPNEDA) | M/s NTPC Renewables Energy Ltd. (SPD) | Tehsil Mau, Dist. Chitrakoot, (U.P.) | 800 | 0 | 800 | 2027-06-03 | 2027-06-03 | Solar
31 | NHPC Limited | NHPC Limited | NP Kunta, Andhra Pradesh | 100 | 0 | 100 | 2023-11-11 | 2026-06-30 | Solar
32 | NHPC Limited | NHPC Limited | Ladeihil,Jaganath Prasad,Ganjam , Odisha | 40 | 0 | 40 | 2025-06-05 | 2026-06-30 | Solar
33 | NHPC Limited | NHPC Limited | Khavda,Bhuj,Kutc h Gujarat | 600 | 0 | 600 | 2026-11-16 | 2026-12-19 | Solar
34 | NHPC Limited | NHPC Limited | West Kallad, Kollam , Kerala | 50 | 0 | 50 | 2026-02-06 | 2026-12-31 | Floating Solar
35 | NHPC Limited | NHPC Limited | Khavda,Bhuj,Kutc h Gujarat | 200 | 0 | 200 | 2025-08-20 | 2026-06-30 | Solar
36 | NHPC Limited | NHPC Limited | Khavda,Bhuj,Kutc h Gujarat | 200 | 0 | 200 | 2026-01-06 | 2026-04-30 | Solar
37 | Mirzapur Solar Park | Bundelkhand Saur Urja Limited – BSUL – a JV of NHPC & UPNEDA | Sherwa, District Mirzapur, Uttar Pradesh | 300 | 100 | 200 | 2025-05-31 | 2026-12-31 | Solar
38 | Floating Solar Park | NHPC Limited | West Kallada, Kerala | 50 | 0 | 50 | 2027-12-31 | 2027-12-31 | solar
39 | Odisha Solar Park | NHPC Limited | Landehill, Ganjam, Odisha | 20 | 0 | 20 | 2025-06-30 | 2026-12-31 | Solar
40 | GUVNL Phase –XVII (Khavda SPP) | SJVN GREEN ENERGY LIMITED | Gujarat | 50 | 0 | 50 | 2025-08-06 | 2026-07-31 | Solar
41 | 50 MW Gujrai Solar Power Station, SJVN Green Energy Limited | SJVN Green Energy Limited | Vill-Gujrai Tehsil-Akbarpur Dist-Kanpur Dehat, Uttar Pradesh | 150 | 0 | 150 | 2027-03-31 | 2027-05-31 | Solar
42 | 100MW Raghanesda Solar Power Project SJVN Green Energy Limited | SJVN Green Energy Limited | Plot-C, Vill-Raghnesda Tehsil-Vav. Dist-Banaskantha, Gujarat | 150 | 0 | 150 | 2027-03-31 | 2027-04-30 | Solar
43 | Gujarat Urja Vikas Nigam Ltd. (GUVNL) Solar Phase XI, Bagodara SPP | SJVN GREEN ENERGY LIMITED | Surendranager, Gujarat | 100 | 0 | 100 | 2025-06-30 | 2026-09-30 | Solar
44 | Dhubri SPP (APDCL) | SJVN GREEN ENERGY LIMITED | Assam | 100 | 0 | 100 | 2025-09-30 | 2026-06-30 | Solar
45 | BBMB 18 MW | SJVN GREEN ENERGY LIMITED | Punjab,Himachal | 100 | 0 | 100 | 2025-03-31 | 2026-09-30 | Solar
46 | BBMB 15 MW | SJVN GREEN ENERGY LIMITED | Himachal Pradesh | 260 | 0 | 260 | 2025-03-31 | 2026-12-31 | Solar
47 | GUVNL Solar Phase - XIV | SJVN GREEN ENERGY LIMITED | Gujarat | 200 | 0 | 200 | 2025-03-31 | 2026-03-31 | Solar
48 | 200 MW Khavda SJVN Solar Power Project Phase 23 | SJVN Limited | Gujarat,Khavda RE park | 200 | 0 | 200 | 2026-08-04 | 2026-11-20 | Solar groundmlount ed project
49 | CPSU SCHEME PHASE –II, Tranche -III | SJVN GREEN ENERGY LIMITED | Rajasthan | 18 | 0 | 18 | 2025-07-07 | 2026-08-30 | Solar
50 | Punjab State Power Corporation Ltd. (PSPCL) ET-2 | SJVN GREEN ENERGY LIMITED | Punjab | 15 | 0 | 15 | 2024-06-23 | 2027-12-31 | Solar
51 | Sonitpur SPP (APDCL) | SJVN GREEN ENERGY LIMITED | Assam | 300 | 0 | 300 | 2025-12-27 | 2027-04-30 | Solar
52 | Rajasthan Urja Vikas Nigam Ltd. (RUVNL) SPP, Nawa | SJVN GREEN ENERGY LIMITED | Rajasthan | 400 | 0 | 400 | 2027-01-17 | 2027-01-31 | Solar
53 | 690 MW ISTS- connected Wind Power Projects (Tranche-XIV) | SJVN Green Energy Ltd | Madhya Pradesh | 700 | 0 | 700 | 2027-03-31 | 2027-03-31 | Wind
54 | Damodar Valley Corporation (DVC) | SPD | Konar, JH | 8 | 0 | 8 | 2025-06-26 | 2026-12-31 | Solar (Ground Mounted)
55 | Jam Khambalia [DVC] | Avaada GJClean Pvt Ltd | Jam Khambalia, Gujarat | 50 | 0 | 50 | 2025-09-30 | 2026-05-31 | Wind
56 | Damodar Valley Corporation (DVC) | SPD | RTPS, WB | 10 | 0 | 10 | 2024-08-03 | 2026-12-31 | Solar (Floating Solar on Raw Water Reservoir of TPP)
57 | Damodar Valley Corporation (DVC) | SPD | MTPS, WB | 14 | 0 | 14 | 2024-08-03 | 2026-12-31 | Solar (Floating Solar on Raw Water Reservoir of TPP)
58 | DVC Floating Solar Park Ph-I | Green Valley Renewable Energy GVREL - A JV of DVC & NTPC Green Energy Limited | Tilaya Dam, Koderma, Jharkhand And, Panchet Dam, Dhanbad, Jharkhand (part of project in West Bengal) | 310 | 0 | 310 | 2027-12-31 | 2027-12-31 | Solar
59 | DVC Floating Solar Park Ph-II | Green Valley Renewable Energy GVREL - A JV of DVC & NTPC Green Energy Limited | Maithon Dam, Dhanbad, Jharkhand (part of project in West Bengal) | 234 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
60 | Damodar Valley Corporation (DVC) | SPD | CTPS, Jharkhand | 10 | 0 | 10 | 2026-01-31 | 2026-12-31 | 10
61 | Damodar Valley Corporation (DVC) | SPD | Rooftop PV Plant at different location of DVC at Jharkand and West Bengal | 10 | 0 | 10 | 2026-01-31 | 2026-12-31 | 10
62 | AM Green Energy Pvt Ltd 300MW Solar Project | AM Green Energy Pvt Ltd, Bikaner | Bikaner, Rajasthan | 300 | 0 | 300 | 2026-11-11 | 2026-11-11 | Solar
63 | NA | Femund Solar Private Limited | Lakadia-II | 350 | 0 | 350 | 2026-08-14 | 2026-08-14 | Solar
64 | NA | Izhma Solar Private Limited | Sirohi, Rajasthan | 350 | 0 | 350 | 2026-11-19 | 2026-11-19 | Solar
65 | SECI | JGRJ One Solar Pvt. Ltd. | District - Bikaner , Rajasthan | 50 | 0 | 50 | 2026-08-22 | 2026-08-22 | Solar
66 | 640 Solar | Axis Energy Ventures India Pvtl.Ltd. | Fatehgarh,Jaisalm er, Rajasthan | 640 | 0 | 0 | 2026-03-31 | 2026-09-30 | Solar
67 | Jhansi Solar Project/TUSCO Ltd. (JV of THDCIL & UPNEDA) | M/s GAIL India Ltd. (SPD) | Tehsil Garautha, Dist. Jhansi, (U.P.) | 600 | 0 | 600 | 2027-12-31 | 2027-12-31 | Solar
68 | IRCON RENEWABLE POWER LIMITED | IRCON RENEWABLE POWER LIMITED | Pavagada, Distt. Tumkur, Karnataka | 500 | 400 | 100 | 2026-06-30 | 2026-07-30 | Solar
69 | Serentica 300 MW Solar plant at Bhadla | NA | Bikampur, Rajasthan | 300 | 0 | 300 | 2028-06-30 | 2028-06-30 | Solar
70 | Serentica Sirohi | NA | Jalore, Rajasthan | 300 | 0 | 300 | 2027-03-31 | 2027-03-31 | Solar
71 | Serentica 900 MW Solar Plant at Fatehgarh | SRIPL5, SRIPL8, SRIPL9 | Fatehgarh, Rajasthan | 900 | 0 | 900 | 2026-08-22 | 2026-06-30 | Solar
72 | Tilaiya | GVREL | State- Jharkhand | 155 | 0 | 155 | 2025-12-31 | 2026-12-31 | Solar PV Project Floating
73 | Panchet-I | GVREL | State- West Bengal | 75 | 0 | 75 | 2025-12-31 | 2027-03-31 | Solar PV Project Floating
74 | Panchet-II | GVREL | State- Jharkhand | 80 | 0 | 80 | 2025-12-31 | 2027-03-31 | Ground & Floating Solar
75 | Bhuj | INGEL | State- Gujarat | 600 | 0 | 600 | 2025-09-30 | 2026-12-31 | Solar PV Project Ground Mounted
76 | Kalyanpur, Dwarka | INGEL | State- Gujarat | 356 | 0 | 356 | 2026-03-31 | 2026-12-31 | Wind
77 | Tuticorin | INGEL | Tamil Nadu | 200 | 0 | 200 | 2027-12-31 | 2026-12-31 | Solar PV Project Ground Mounted
78 | Khavda IX | NGEL | Gujarat | 245 | 0 | 245 | 2026-01-10 | 2027-03-31 | Solar
79 | Lalitpur I & II | NGEL | UP | 600 | 0 | 600 | 2027-01-06 | 2027-03-31 | Solar
80 | Chitrakoot I | NGEL | UP | 400 | 0 | 400 | 2027-01-06 | 2027-03-31 | Solar
81 | Bikaner III | NGEL | Rajasthan | 250 | 0 | 250 | 2027-01-02 | 2027-03-31 | Solar
82 | SECI Ltd. | Clean Renewable Energy (Barmer) Private Limited (SPV of Hero Solar Energy Private Limited) | Kurnool, Andhra Pradesh | 120 | 0 | 120 | 2026-10-27 | 2026-10-27 | Hybrid
83 | NHPC Ltd. | Clean Renewable Energy AP One Private Limited (SPV of Hero Solar Energy Private Limited) | Bidar, Karnataka | 100 | 0 | 100 | 2026-12-23 | 2026-12-23 | Hybrid
84 | SECI Ltd. | Clean Renewable Energy Hybrid Eight Private Limited (SPV of Hero Solar Energy Private Limited) | Bidar, Karnataka | 250 | 0 | 250 | 2026-11-07 | 2026-11-07 | Solar with ESS
85 | SECI Ltd. | Clean Renewable Energy Hybrid Eleven Private Limited (SPV of Hero Solar Energy Private Limited) | Lakadia, Gujarat | 270 | 0 | 270 | 2027-03-31 | 2027-03-31 | Solar with ESS
86 | NTPC Ltd. | Clean Renewable Energy Hybrid Five Private Limited (SPV of Hero Solar Energy Private Limited) | Lakadia, Gujarat | 120 | 0 | 120 | 2027-04-11 | 2027-04-11 | Hybrid
87 | SECI Ltd. | Clean Renewable Energy Hybrid Nine Private Limited (SPV of Hero Solar Energy Private Limited) | Lakadia, Gujarat | 100 | 0 | 0 | 2027-06-30 | 2027-06-30 | Hybrid
88 | SECI Ltd. | Clean Renewable Energy Hybrid One Private Limited (SPV of Hero Solar Energy Private Limited) | Lakadia, Gujarat | 120 | 0 | 0 | 2027-10-31 | 2027-10-31 | Hybrid
89 | SJVN Ltd. | Clean Renewable Energy Hybrid Thirteen Private Limited (SPV of Hero Solar Energy Private Limited) | Ananthapuram, Andhra Pradesh | 120 | 0 | 120 | 2027-05-31 | 2027-05-31 | Hybrid
90 | SJVN Ltd. | Clean Renewable Energy Hybrid Three Private Limited (SPV of Hero Solar Energy Private Limited) | Nandyal, Andhra Pradesh | 120 | 0 | 120 | 2026-05-13 | 2026-05-13 | Hybrid
91 | SJVN Ltd. | Clean Renewable Energy Hybrid Twelve Private Limited (SPV of Hero Solar Energy Private Limited) | Ananthapuram, Andhra Pradesh | 120 | 0 | 120 | 2027-03-24 | 2027-03-24 | Hybrid
92 | SJVN Ltd. | Clean Solar Power (Baniyana) Private Limited (SPV of Hero Solar Energy Private Limited) | Bidar, Karnataka | 150 | 0 | 150 | 2026-05-21 | 2026-05-21 | Hybrid
93 | Not Finalized | SPV of Hero Solar Energy Private Limited | Lakadia, Gujarat | 150 | 0 | 0 | 2027-10-31 | 2027-10-31 | Solar
94 | Not Finalized | SPV of Hero Solar Energy Private Limited | Bidar, Karnataka | 277.8 | 0 | 0 | 2027-05-31 | 2027-05-31 | Hybrid
95 | Not Finalized | SPV of Hero Solar Energy Private Limited | Bijapur, Karnataka | 350 | 0 | 0 | 2027-06-28 | 2027-06-28 | Solar with ESS
96 | Not Finalized | SPV of Hero Solar Energy Private Limited | Kadapa, Andhra Pradesh | 450 | 0 | 450 | 2028-06-30 | 2028-06-30 | Solar with ESS
97 | SECI 1200MW ISTS- connected Wind Solar Hybrid Power Projects (Tranche-VIII) | Asurari Renewables India Project Pvt Ltd | Rajasthan (Solar) , Karnataka (Wind) | 300 | 0 | 300 | PPA Pending | PPA Pending | Hybrid
98 | SJVN 600MW ISTS- connected Wind Power Projects (Tranche-I) | Diyos Renewables India Project Pvt Ltd | Vijayapura, Karnataka | 100 | 0 | 100 | 17-Jan-27 (Tentative) | 2027-02-27 | Wind
99 | SECI 1500MW ISTS- connected Solar Power Projects (Tranche-XIII) | Tejorupa Renewables India Project Pvt Ltd | Vill - Balai Kesharpura, Tehsil - Sheo, Dis-Barmer, State - Rajasthan | 250 | 0 | 250 | 2026-11-07 | 2027-01-25 | Solar
100 | SECI | Scatec India Renewables One Pvt Ltd | Khustagi-Karnataka | 300 | 0 | 300 | 2027-12-31 | 2027-12-31 | Wind
101 | SJVNL | Solarcraft Power India 16 Pvt. Ltd. | Kalaburagi District, Karnataka | 150 | 0 | 150 | 2026-06-30 | 2026-06-30 | Hybrid (FDRE)
102 | NHPC | Solarcraft Power India 20 Pvt. Ltd. | Kalaburagi District, Karnataka | 50 | 0 | 50 | 2026-12-17 | 2026-12-17 | Hybrid
103 | Amazon | Solarcraft Power India 7 Pvt. Ltd. | Kalaburagi District, Karnataka | 100 | 0 | 100 | 2027-06-01 | 2027-06-01 | Wind
104 | Adani Green Energy Limited | Adani Green Energy Limited | Gujarat | 1000 | 535 | 475 | 2025-12-31 | 2026-12-31 | Hybrid
105 | Adani Green Energy Limited | Adani Green Energy Limited | Gujarat | 1050 | 419 | 631 | 2025-12-31 | 2026-06-30 | Hybrid
106 | Adani Green Energy Limited | Adani Green Energy Limited | Gujarat | 1225 | 899 | 425 | 2025-03-31 | 2026-12-31 | Hybrid
107 | Adani Green Energy Limited | Adani Green Energy Limited | Gujarat | 1530 | 0 | 1530 | 2028-05-31 | 2028-12-31 | Hybrid
108 | ADANI GREEN ENERGY THIRTY TWO LIMITED | ADANI GREEN ENERGY THIRTY TWO LIMITED | Gujarat | 261 | 0 | 261 | 2026-06-30 | 2026-06-30 | Wind
109 | ADANI RENEWABLE ENERGY EIGHT LIMITED | ADANI RENEWABLE ENERGY EIGHT LIMITED | Gujarat | 115 | 0 | 115 | 2026-06-30 | 2026-06-30 | Solar
110 | Adani Renewable Energy Holding Eighteen Limited (AREH18L) | Adani Renewable Energy Holding Eighteen Limited (AREH18L) | Rajasthan | 50 | 0 | 50 | 2027-03-31 | 2027-03-31 | Solar
111 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Gujarat | 2000 | 1250 | 750 | 2026-10-31 | 2026-12-31 | Solar
112 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Gujarat | 500 | 0 | 500 | 2024-02-28 | 2026-12-31 | Solar
113 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Rajasthan | 500 | 0 | 500 | 2025-10-31 | 2026-06-30 | Solar
114 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Rajasthan | 717 | 0 | 717 | 2029-12-31 | 2029-12-31 | Solar
115 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Rajasthan | 765 | 0 | 765 | 2030-03-31 | 2030-03-31 | Solar
116 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Rajasthan | 500 | 0 | 500 | 2028-12-31 | 2028-12-31 | Solar
117 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Rajasthan | 500 | 0 | 500 | 2028-12-31 | 2028-12-31 | Solar
118 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Rajasthan | 250 | 0 | 250 | 2028-12-31 | 2028-12-31 | Solar
119 | Adani Renewable Energy Holding Four Limited | Adani Renewable Energy Holding Four Limited | Rajasthan | 284 | 0 | 284 | 2030-03-31 | 2030-03-31 | Solar
120 | Adani Renewable Energy Holding Seventeen Private Limited | Adani Renewable Energy Holding Seventeen Private Limited | Rajasthan | 600 | 0 | 600 | 2025-12-31 | 2026-06-30 | Solar
121 | Adani Renewable Energy Park Rajasthan Limited | Adani Renewable Energy Park Rajasthan Limited | Rajasthan | 1000 | 0 | 1000 | 2030-03-31 | 2030-03-31 | Solar
122 | Adani Renewable Energy Park Rajasthan Limited | Adani Renewable Energy Park Rajasthan Limited | Rajasthan | 1000 | 0 | 1000 | 2030-03-31 | 2030-03-31 | Solar
123 | ADANI RENEWABLE ENERGY TWO LIMITED | ADANI RENEWABLE ENERGY TWO LIMITED | Rajasthan | 595 | 0 | 595 | 2029-12-31 | 2029-12-31 | Wind
124 | ADANI RENEWABLE ENERGY TWO LIMITED | ADANI RENEWABLE ENERGY TWO LIMITED | Rajasthan | 600 | 0 | 600 | 2029-12-31 | 2029-12-31 | Wind
125 | Adani Solar Energy AP Three Ltd. | Adani Solar Energy AP Three Ltd. | Rajasthan | 150 | 0 | 150 | 2026-08-31 | 2026-09-30 | Solar
126 | SIROHI SOLAR POWER PROJECT (300 MW stand alone ISTS connectivity Solar Power Project) | CESC Limited (Developer Company) | Sheoganj Tehsil, District Sirohi, Rajasthan State | 300 | 0 | 300 | 2027-03-24 | 2027-03-24 | Solar
127 | CESC | HPPD - Bhojraj Renewables Energy Private Limited | Co-located Hybrid at Sitamau, Mandsaur, Madhya Pradesh | 300 | 0 | 300 | 2026-12-31 | 2026-12-31 | Hybrid
128 | Purvah Bikaner One Solar Power Project | Purvah Green Power Private Limited (Developer Company) | Village Sodhwali, Bikaner District, Rajasthan | 300 | 0 | 300 | 2030-03-31 | 2030-03-31 | Hybrid
129 | Purvah Bikaner Two Solar Power Project | Purvah Green Power Private Limited (Developer Company) | Village Binjharwali, Bikaner District, Rajasthan | 300 | 0 | 300 | 2030-03-31 | 2030-03-31 | Solar
130 | Purvah Raghanesda One Solar Power Project | Purvah Green Power Private Limited (Developer Company) | Village Raghanesda , Banaskantha, Gujarat | 300 | 0 | 300 | 2028-04-01 | 2028-04-01 | Solar
131 | Purvah Bellary One Solar Power Project | Purvah Green Power Private Limited (Developer Company) | Village Moregeri, District Vijayanagara, Karnataka | 300 | 0 | 300 | 2028-09-01 | 2028-09-01 | Solar
132 | Purvah Davangere One Wind Power Project | Purvah Green Power Private Limited (Developer Company) | Village Kanchikere, District Davangere, Karnataka | 300 | 0 | 300 | 2028-04-01 | 2028-04-01 | Wind
133 | Purvah Ananthapuram One Solar Power Project | Purvah Green Power Private Limited (Developer Company) | Village Palthur, District Ananthapuram, Andhra Pradesh | 300 | 0 | 300 | NA | NA | Solar
134 | Purvah Kurnool One RE Power Project | Purvah Green Power Private Limited (Developer Company) | Village Karumanchi, District Kurnool, Andhra Pradesh | 300 | 0 | 300 | NA | NA | Solar
135 | Purvah Kadapa One RE Power Project | Purvah Green Power Private Limited (Developer Company) | Village Kolumula Palli, District Kadapa, Andhra Pradesh | 300 | 0 | 300 | NA | NA | Solar
136 | PURVAH BHUJ ONE WIND POWER PROJECT (99 MW Wind Power Project with ISTS connectivity) | Purvah Green Power Private Limited (Developer Company) | Village Dayapar, Kachchh District, Gujarat State | 99 | 0 | 99 | 2026-11-19 | 2026-11-19 | Wind
137 | PURVAH NAGAUR SOLAR POWER PROJECT (300 MW stand alone ISTS connectivity Solar Power Project) | Purvah Green Power Private Limited (Developer Company) | Village Charnisar, Nagaur District, Rajasthan State | 300 | 0 | 300 | 2027-09-01 | 2027-09-01 | Solar
138 | PURVAH JAMNAGAR ONE WIND POWER PROJECT (297 MW stand alone ISTS connectivity Wind Power Project) | Purvah Green Power Private Limited (Developer Company) | Village Hadiyana, Jamnagar District, Gujarat State | 297 | 0 | 297 | 2028-01-01 | 2028-01-01 | Wind
139 | PURVAH BIJAPUR ONE WIND POWER PROJECT (351 MW stand alone ISTS connectivity Wind Power Project) | Purvah Green Power Private Limited (Developer Company) | Village Dhavalagi, Bijapur District, Karnataka State | 351 | 0 | 351 | 2026-07-31 | 2027-08-31 | Wind
140 | PURVAH BIJAPUR TWO WIND POWER PROJECT (250.8 MW stand alone ISTS connectivity Wind Power Project) | Purvah Green Power Private Limited (Developer Company) | Village Hunsagi, Bijapur District, Karnataka State | 250.8 | 0 | 250.8 | 2027-08-31 | 2027-08-31 | Wind
141 | PURVAH ANATAPURAM TWO WIND POWER PROJECT (349.8 MW stand alone ISTS connectivity Wind Power Project) | Purvah Green Power Private Limited (Developer Company) | Village Devireddypalli, Anantapuram District, Andhra Pradesh State | 349.8 | 0 | 349.8 | 2027-01-31 | 2027-01-31 | Wind
142 | PURVAH PACHORA ONE WIND POWER PROJECT (297 MW stand alone ISTS connectivity Wind Power Project) | Purvah Green Power Private Limited (Developer Company) | Village Dhandheda Kanad, Agar Malwa District, Madhya Pradesh State | 297 | 0 | 297 | 2027-08-31 | 2027-08-31 | Wind
143 | Purvah Renewable Bellary One Wind Power Project | Purvah Renewable Power Private Limited (Developer Company) | Village Ittigi, District Vijayanagara, Karnataka | 300 | 0 | 300 | 2028-09-01 | 2028-09-01 | Wind
144 | SHN Green Ramgarh One Wind Power Project (297 MW stand alone ISTS connectivity Wind) | SHN Green Power Private Limited (Developer Company) | Village Ramgarh, Jaislmer District, Rajasthan State | 297 | 0 | 297 | 2030-03-31 | 2030-03-31 | Wind
145 | NPCL | SPV - Deshraj Solar Energy Private Limited | Village Ralla, Anantapuram District, Andhra Pradesh State | 300 | 0 | 300 | 2027-01-31 | 2027-01-31 | Wind
146 | NPCL | SPV - Deshraj Solar Energy Private Limited | Karnisar Bhatiyan, Bikaner, Rajasthan | 150 | 0 | 150 | 2027-01-31 | 2027-01-31 | Solar
147 | CESC | SPV - HRP Green Power Private Limited | Village Nokh and Geleba Camp, Tehsil Bap, District Phalodi, Rajasthan State | 300 | 0 | 300 | 2026-04-03 | 2026-04-03 | Solar
148 | Vital Green Kurnool One Wind Power Project | Vital Green Power Private Limited (Developer Company) | Village Pattikonda, District Kurnool, Andhra Pradesh | 300 | 0 | 300 | NA | NA | Wind
149 | SECI Wind XIV | Apraava Energy Private Limited | Aski Village, Vijayapura District, Karnataka State | 300 | 0 | 300 | 27-12- 2025/17- 01-2027 | 2027-03-16 | Wind
150 | NHPC Solar ISTS-I | Apraava Energy Private Limited | Bhanipura Village, Bikaner District, Rajasthan State | 250 | 0 | 250 | 17-04- 2026/31- 08-2026 | 2026-10-31 | Solar
151 | NTPC Solar ISTS-I | Apraava Energy Private Limited | Bhanipura Village, Bikaner District, Rajasthan State | 300 | 0 | 300 | 30-06- 2026/31- 08-2026 | 2026-09-30 | Solar
152 | NTPC Solar ISTS-III | Apraava Energy Private Limited | Bhanipura Village, Bikaner District, Rajasthan State | 50 | 0 | 50 | PPA yet to signed/ 30.06.2027 | 2027-08-30 | Solar
153 | 50 MW ISTS- connected Wind Power Projects (Tranche-XVI) | Powerica Limited | Jam Khambhaliya, Gujarat | 50 | 0 | 50 | 2025-12-31 | 24.01.2026 - 50 MW | Wind
154 | 50 MW ISTS- connected Wind Power Projects (Tranche-XVII) | Powerica Limited | Jam Khambhaliya, Gujarat | 50 | 0 | 50 | 2026-10-14 | 2026-10-14 | Wind
155 |  | Auxo Sunlight Private Limited | Rajasthan | 300 | 0 | 300 | 2026-12-30 | 2026-12-30 | Solar
156 | SECI | IB Vogt Solar Seven Pvt.Ltd. | Rajasthan | 300 | 200 | 100 | 2026-06-30 | 2026-04-30 | Solar
157 | PSPCL | ReNew Dinkar Jyoti Pvt Ltd. | Rajasthan | 100 | 0 | 100 | 2025-12-31 | 2026-08-31 | Solar
158 | Merchant | ReNew Green Energy Solutions Pvt ltd | Maharashtra | 237 | 0 | 237 | 2027-03-31 | 2027-03-31 | Wind
159 | Merchant | ReNew Green Energy Solutions Pvt ltd | Maharashtra | 197 | 124 | 73 | 2025-09-30 | 2026-04-30 | Hybrid
160 | SECI | ReNew Naveen Urja Private Limited | Karnataka | 297.5 | 0 | 297.5 | 2024-07-01 | 2026-03-31 | Wind
161 | Merchant | ReNew Samir Urja Pvt Ltd | Madhya Pradesh | 300 | 0 | 300 | 2026-03-31 | 2026-09-30 | Wind
162 |  | ReNew Solar (Shakti Eight) Pvt. ltd. | Gujarat | 200 | 0 | 200 | 2026-09-01 | 2026-09-01 | Solar
163 |  | ReNew Solar (Shakti Eight) Pvt. ltd. | Gujarat | 100 | 0 | 100 | 2026-09-01 | 2026-09-01 | Solar
164 | Merchant | ReNew Solar (Shakti Five) Private Limited | Rajasthan | 400 | 0 | 400 | 2026-06-30 | 2026-04-30 | Solar
165 |  | ReNew Solar (Shakti Six) Pvt. ltd. | Rajasthan | 1000 | 0 | 1000 | 2026-06-30 | 600MW to be commissioi ned in 31/05/26 | Solar
166 |  | ReNew Solar (Shakti Six) Pvt. ltd. (400+400) | Rajasthan | 400 | 0 | 400 | 2029-07-20 | 2029-07-20 | Solar
167 |  | ReNew Solar (Shakti Six) Pvt. ltd. (400+400) | Rajasthan | 400 | 0 | 400 | 2029-07-20 | 2029-07-20 | Solar
168 | NTPC | ReNew Solar Power P. Ltd | Rajasthan | 400 | 0 | 400 | 2027-03-01 | 2027-03-01 | Solar
169 | SECI | ReNew Solar Power P. Ltd | Rajasthan | 300 | 0 | 300 | 2030-03-31 | 2030-03-31 | Solar
170 | SJVN | ReNew Solar Power P. Ltd | Rajasthan | 200 | 0 | 200 | 2030-03-31 | 2030-03-31 | Solar
171 | SJVN | ReNew Solar Power P. Ltd | Rajasthan | 300 | 0 | 300 | 2030-03-31 | 2030-03-31 | Solar
172 | NTPC | ReNew Solar Power Private Limited | Karnataka | 100 | 0 | 100 | 2027-07-31 | 2027-07-31 | Wind
173 | NTPC | ReNew Solar Power Private Limited | Karnataka | 100 | 0 | 100 | 2027-07-31 | 2027-07-31 | Wind
174 | NTPC | ReNew Solar Power Private Limited | Andhra Pradesh | 400 | 0 | 400 | Ananthapu ram-II- 30/06/27 | 2030-03-31 | Wind
175 | NHPC | ReNew Solar Power Private Limited | Gujarat | 250 | 0 | 250 | 2030-09-30 | 2030-09-30 | Hybrid
176 | REMCL | RENEW SOLAR POWER PRIVATE LIMITED | MAHARASHTRA | 200 | 0 | 200 | 2026-11-30 | 2026-11-30 | Wind
177 | SJVN FDRE | RENEW SOLAR POWER PRIVATE LIMITED | RAJASTHAN | 70 | 0 | 70 | 2028-03-31 | 2028-03-31 | Solar
178 | SJVN FDRE | RENEW SOLAR POWER PRIVATE LIMITED | RAJASTHAN | 300 | 0 | 300 | 2027-01-31 | 2027-01-31 | Solar
179 | SJVN FDRE | RENEW SOLAR POWER PRIVATE LIMITED | RAJASTHAN | 70 | 0 | 70 | 2027-01-31 | 2027-01-31 | Solar
180 | REMCL | RENEW SOLAR POWER PRIVATE LIMITED | MAHARASHTRA | 100 | 0 | 100 | 2026-11-30 | 2026-11-30 | Wind
181 | NHPC | ReNew Solar Power Private Limited | RAJASTHAN | 300 | 0 | 300 | 2027-03-31 | 2027-03-31 | Solar
182 | NHPC | ReNew Solar Power Private Limited | RAJASTHAN | 300 | 0 | 300 | 2027-03-31 | 2027-03-31 | Solar
183 | NHPC | ReNew Solar Power Private Limited | RAJASTHAN | 300 | 0 | 300 | 2027-03-31 | 2027-03-31 | Solar
184 | NHPC | ReNew Solar Power Private Limited | RAJASTHAN | 300 | 0 | 300 | 2027-04-30 | 2027-04-30 | Solar
185 | NHPC | ReNew Solar Power Private Limited | RAJASTHAN | 300 | 0 | 300 | 2027-04-30 | 2027-04-30 | Solar
186 | SECI | ReNew Solar Power Private Limited | Maharashtra | 300 | 128 | 172 | 2022-12-31 | 2026-02-10 | Wind
187 | NTPC | ReNew Solar Power Private Limited | RAJASTHAN | 300 | 0 | 300 | 2027-04-30 | 2027-04-30 | Solar
188 | NHPC | ReNew Solar Power Private Limited | RAJASTHAN | 150 | 0 | 150 | 2027-04-30 | 2027-04-30 | Solar
189 | NHPC | ReNew Solar Power Private Limited | RAJASTHAN | 150 | 0 | 150 | 2027-04-30 | 2027-04-30 | Solar
190 | SECI | ReNew Solar Power Private Limited (2 x 300) | Rajasthan | 300 | 0 | 300 | 2026-03-01 | 2026-11-30 | Solar
191 | SECI | ReNew Solar Power Private Limited (2 x 300) | Rajasthan | 300 | 0 | 300 | 2026-11-30 | 2027-01-31 | Solar
192 | NTPC | ReNew Solar Power Pvt Ltd | Rajasthan | 300 | 0 | 300 | 2027-06-01 | 2027-06-01 | Solar
193 | SECI | ReNew Solar Power Pvt Ltd | Rajasthan | 300 | 0 | 300 | 2029-12-31 | 2029-12-31 | Solar
194 | REMCL | ReNew Solar Power Pvt Ltd | Rajasthan | 200 | 0 | 200 | 2030-09-01 | 2030-09-30 | Solar
195 | NTPC | ReNew Solar Power Pvt Ltd | Rajasthan | 400 | 0 | 400 | 2030-03-31 | 2030-03-31 | Solar
196 | NTPC | ReNew Solar Power Pvt Ltd | Rajasthan | 300 | 0 | 300 | 2030-03-01 | 2030-03-31 | Solar
197 |  | ReNew Solar Power Pvt Ltd | Rajasthan | 100 | 0 | 100 | 2030-03-01 | 2030-03-31 | Solar
198 |  | ReNew Solar Power Pvt Ltd | Rajasthan | 100 | 0 | 100 | 2030-03-01 | 2030-03-31 | Solar
199 |  | ReNew Solar Power Pvt Ltd | Rajasthan | 100 | 0 | 100 | 2030-03-01 | 2030-03-31 | Solar
200 |  | ReNew Solar Power Pvt Ltd | Rajasthan | 200 | 0 | 200 | 2030-03-01 | 2030-03-31 | Solar
201 |  | ReNew Solar Power Pvt Ltd | Rajasthan | 200 | 0 | 200 | 2030-03-01 | 2030-03-31 | Solar
202 | NTPC | ReNew Solar Power Pvt Ltd | Rajasthan | 250 | 0 | 250 | 2030-12-31 | 2030-12-31 | Solar
203 | NTPC | ReNew Solar Power Pvt Ltd | Rajasthan | 300 | 0 | 300 | 2031-03-01 | 2031-03-31 | Solar
204 | NTPC | ReNew Solar Power Pvt Ltd | Rajasthan | 300 | 0 | 300 | 2030-12-31 | 2030-12-31 | Solar
205 | SJVN | ReNew Solar Power Pvt Ltd | Rajasthan | 200 | 0 | 200 | 2031-03-01 | 2031-03-31 | Solar
206 | SJVN | ReNew Solar Power Pvt Ltd | Rajasthan | 200 | 0 | 200 | 2031-03-01 | 2031-03-31 | Solar
207 |  | ReNew Solar Power Pvt Ltd | Gujarat | 300 | 0 | 300 | 2027-09-01 | 2027-09-01 | Solar
208 |  | ReNew Solar Power Pvt Ltd | Gujarat | 300 | 0 | 300 | 2027-11-01 | 2027-11-01 | Solar
209 |  | ReNew Solar Power Pvt Ltd | Gujarat | 100 | 0 | 100 | 2028-02-01 | 2028-02-01 | Solar
210 |  | ReNew Solar Power Pvt Ltd | Gujarat | 100 | 0 | 100 | 2028-02-01 | 2028-02-01 | Solar
211 |  | ReNew Solar Power Pvt Ltd | Gujarat | 200 | 0 | 200 | 2028-01-01 | 2028-01-01 | Solar
212 |  | ReNew Solar Power Pvt Ltd | Gujarat | 300 | 0 | 300 | 2029-02-28 | 2029-02-28 | Solar
213 |  | ReNew Solar Power Pvt Ltd | Gujarat | 300 | 0 | 300 | 2029-02-28 | 2029-02-28 | Solar
214 | SECI | ReNew Solar Power Pvt Ltd | Gujarat | 200 | 0 | 200 | 2029-02-28 | 2029-02-28 | Solar
215 |  | ReNew Solar Power Pvt Ltd | Gujarat | 100 | 0 | 100 | 2029-02-28 | 2029-02-28 | Solar
216 |  | ReNew Solar Power Pvt Ltd | Gujarat | 100 | 0 | 100 | 2029-02-28 | 2029-02-28 | Solar
217 |  | ReNew Solar Power Pvt Ltd | Madhya Pradesh | 200 | 0 | 200 | 2027-09-01 | 2027-09-01 | Solar
218 |  | Renew Sun Power Private Limited | Rajasthan | 300 | 0 | 300 | 2026-11-01 | 2026-11-30 | Solar
219 | Merchant | ReNew Tej Shakti Pvt. Ltd. | Maharashtra | 300 | 0 | 300 | 2025-06-30 | 2026-03-31 | Wind
220 | Merchant | ReNew Urja Shachar Pvt Ltd | Madhya Pradesh | 300 | 0 | 300 | 2025-06-01 | 2026-09-30 | Wind
221 |  | ReNew Vayu Energy Private Limited | Karnataka | 300 | 0 | 300 | 2027-03-01 | 2027-03-01 | Hybrid
222 |  | ReNew Vikram Shakti Private Limited | Andhra Pradesh | 1484 | 0 | 685 | 2026-06-30 | 2026-10-27 | Hybrid
223 |  | ReNew Vikram Shakti Private Limited | Andhra Pradesh | 160 | 0 | 160 | 2028-02-01 | 2028-02-01 | Hybrid
224 | Merchant | ReNew Vikram Shakti Private Ltd | Andhra Pradesh | 140 | 0 | 140 | 2028-02-01 | 2028-02-01 | Hybrid
225 | Merchant | ReNew Wind Energy AP5 Private Ltd | Karnataka | 231.8 | 0 | 231.8 | 2028-03-31 | 2028-03-31 | Wind
226 | Azure Power Fifty One Private Limited | Azure Power Fifty One Private Limited | Bhadla-V ISTS - Rajasthan | 600 | 0 | 600 | 2031-09-30 | 2031-09-30 | Solar
227 | Manufacturing plant linked Solar Project scheme | Azure Power India Private Limited | Bhadla-II, Rajasthan | 167 | 0 | 167 | 2028-09-30 | 2028-09-30 | Solar
228 | Manufacturing plant linked Solar Project scheme | Azure Power India Private Limited | Bhadla-II, Rajasthan | 100 | 0 | 100 | 2028-09-30 | 2028-09-30 | Solar
229 | Manufacturing plant linked Solar Project scheme | Azure Power India Private Limited | Bhadla-II, Rajasthan | 333 | 0 | 333 | 2028-09-30 | 2028-09-30 | Solar
230 | Manufacturing plant linked Solar Project scheme | Azure Power India Private Limited | Bhadla-II, Rajasthan | 50 | 0 | 50 | 2028-03-15 | 2028-03-15 | Solar
231 | 1200 MW ISTS- connected Wind Power Projects (Tranche-XI) | Azure Power lndia Pvt Ltd | Koppal, Karnataka | 120 | 0 | 120 |  |  | Wind
232 | Azure Power Sixty Three Private Limited | Azure Power Sixty Three Private Limited | Raghanesda - Gujarat | 300 | 0 | 300 | 2027-12-31 | 31-12-2027 (300 MW) | Solar
233 | Azure Power Sixty Three Private Limited | Azure Power Sixty Three Private Limited | Lakadia-II ISTS - Gujarat | 300 | 0 | 300 | 2028-12-31 | 2028-12-31 | Hybrid
234 | RDS Solar Park Private Limited , 350 MW Solar | RDS Solar Park Private Limited | Lakadia PS, Gujarat | 20 | 0 | 20 | 2026-06-01 | 2026-06-01 | Solar
235 | Wind Power Project | VENA ENERGY AURA PRIVATE LIMITED | Koppal, Karnataka | 100 | 0 | 100 | 2026-12-31 | 2027-06-30 | Hybrid
236 | Wind Power Project | VENA ENERGY AURA PRIVATE LIMITED | Koppal, Karnataka | 24 | 0 | 24 | 2027-12-31 | 2027-12-31 | Wind
237 | Solar Power Project | VENA ENERGY CLEAN POWER PRIVATE LIMITED | Veloda, Gujarat | 40 | 0 | 40 | 2022-03-25 | 2027-12-31 | Solar
238 | Solar Power Project | VENA ENERGY RENEWABLES URJA PRIVATE LTD | Dholera, Gujarat | 100 | 0 | 100 | 2027-12-31 | 2027-12-31 | Solar
239 | Jindal Renewables - Wind Project - C&I | Jindal Green Wind 1 Private Limited | Tawargere, Karnataka | 400 | 0 | 400 | 2025-12-31 | 2026-04-15 | Wind
240 | Jindal Renewables - Wind Project - C&I | Jindal Green Wind 1 Private Limited | Karur, Tamilnadu | 300 | 0 | 300 | 2025-12-25 | 2026-04-15 | Wind
241 | Jindal Renewables - Wind Project - C&I | Jindal Green Wind 1 Private Limited | Kanakagiri, Karnataka | 300 | 0 | 300 | 2025-12-31 | 2026-04-15 | Wind
242 | Jindal Renewables - Wind Project - C&I | Jindal Green Wind 1 Private Limited | Karur, Tamilnadu | 50 | 0 | 50 | Dec-28 | 2026-12-31 | Wind
243 | Jindal Renewables - Solar Project - C&I | Sunbreeze Renewables Nine Private Limited | Bikaner Rajasthan | 1000 | 0 | 1000 | 2026-08-22 | 2026-04-15 | Solar
244 | Jindal Renewables - Solar Project - C&I | Sunbreeze Renewables Nine Private Limited | Bikaner Rajasthan | 400 | 0 | 400 | 2026-08-22 | 2026-04-15 | Solar
245 | SJVN Limited | Furies Solren Private Limited | Bikaner, Rajasthan | 300 | 0 | 300 | 2026-11-11 | 2027-03-31 | Solar
246 | NTPC Limited | Furies Solren Private Limited | Bikaner, Rajasthan | 300 | 0 | 300 | 2026-11-11 | 2027-03-31 | Solar
247 | NHPC Limited | Hazel Hybren Private Limited | Bikaner, Rajasthan | 300 | 0 | 300 | 2026-05-01 | 2026-05-01 | Solar
248 | NTPC Limited | Illuminate Hybren Private Limited | Sirohi, Rajansthan | 176 | 0 | 176 | 2027-03-24 | 2027-03-24 | Solar
249 | NTPC Limited | Illuminate Hybren Private Limited | Sirohi, Rajansthan | 120 | 0 | 120 | 2027-03-24 | 2027-03-24 | Solar
250 | NHPC Limited | Illuminate Hybren Private Limited | Davangere, Karnataka | 240 | 0 | 240 | 2027-03-22 | 2027-03-22 | Hybrid
251 | NHPC Limited | Migos Hybren Private Limited | Sikar, Rajasthan | 600 | 0 | 600 | 2028-12-31 | TBD after PPA execution | Solar
252 | 184MW Wind Portion at Gadag of Solar Wind Hybrid Project for Captive Customer | ABREL (RJ) PROJECTS LIMITED | Mundargi, Gadag, KARNATAKA | 184 | 0 | 184 | 2025-12-30 | 2027-06-23 | Wind
253 | 184MW Wind Portion at Koppal of Solar Wind Hybrid Project for Ultratech | ABREL (RJ) PROJECTS LIMITED | Mullur, Koppal, KARNATAKA | 184 | 0 | 184 | 2025-12-27 | 2027-05-16 | Wind
254 | 260 MW Solar Wind Hybrid Project for Ultratech + 52.7 MW Wind under clause 5.2 of GNA regulation | ABREL (RJ) PROJECTS LIMITED | Barmer, RAJASTHAN | 260 | 0 | 260 | 2026-08-22 | 130 MW (31.05.202 6); 130 MW (30.06.202 6); 52.7 MW (22.08.202 6) | Wind-Solar Hybrid
255 | 52.7 MW Wind under clause 5.2 of GNA regulation | ABREL (RJ) PROJECTS LIMITED | Barmer, RAJASTHAN | 52.7 | 0 | 52.7 | 2026-08-22 | 2026-08-22 | Wind
256 | 314 MW Solar Wind Hybrid Project for Ultratech | ABREL (RJ) PROJECTS LIMITED | Ashapar, Kutch, GUJARAT | 314 | 0 | 314 | 2026-11-24 | 2026-05-31 | Hybrid
257 | 102MW Wind Portion at Gadag of Solar Wind Hybrid Project for Captive Customer | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | Mundargi, Gadag, KARNATAKA | 102 | 0 | 102 | 2025-12-31 | 2027-04-08 | Wind
258 | 102 MW Wind Portion at Koppal of Solar Wind Hybrid Project for Captive Customer | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | Mullur, Koppal, KARNATAKA | 102 | 0 | 102 | 2025-12-31 | 2027-03-05 | Wind
259 | 390 MW Solar Wind PSP Storage Hybrid Captive Project for Captive Customer | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | Barmer, RAJASTHAN | 390 | 0 | 390 | 2026-08-22 | 200 MW (31.05.202 6); 162 MW (30.06.202 6); 25 MW (31.12.202 6) | Hybrid
260 | 362 MW Solar Wind PSP Storage Hybrid Captive Project for Hindalco Industries Limited | ADITYA BIRLA RENEWABLES SUBSIDIARY LIMITED | Ashapar, Kutch, GUJARAT | 362 | 0 | 362 | 2026-12-18 | 2027-03-31 | Hybrid
261 | REMCL | Project Nine Renewable Power Private Limited | Bhadla, Rajasthan Sudi, Karnataka Aspiri, Andhra Pradesh | 300 | 0 | 300 | 31-12- 2026(Solar) 31-03-2026(Wind) | 31-12- 2026(Solar) 31-03-2026(Wind) | RTC
262 | NHPC | JGRJ Two Solar Pvt. Ltd. | District - Bikaner , Rajasthan | 70 | 0 | 70 | 2025-03-31 | 2026-03-31 | Solar
263 | Northern Railway | Sprng Akshaya Urja Pvt. Ltd. | Solar - Rajasthan, Wind - Madhya Pradesh and Tamil Nadu | 417.8 | 0 | 365 | 2025-12-26 | Solar: Subject to issuance of sec 68 (impaccted due to GIB) | RTC
264 | GUVNL | Sprng Green Power Pvt. Ltd. | Banas Kantha , Gujarat | 300 | 145 | 155 | 2024-10-28 | 2026-04-26 | Solar
265 | SECI | Sprng Power Earth Pvt. Ltd. | Banaskantha , Gujarat | 250 | 0 | 250 | 2026-03-31 | 2026-08-31 | Solar
266 | NHPC | Sprng Power Pvt. Ltd. | Fatehgarh, Rajasthan | 250 | 0 | 250 | 2026-04-25 | 2026-04-25 | Solar
267 | NTPC | Sprng Vayu Vidyut Pvt. Ltd. | Solar - Bhardava, Banaskantha, Gujarat Wind - Ahu, Dhar, Madhya Pradesh | 250 | 0 | 250 | 2026-06-29 | 2026-06-29 | Hybrid
268 | NTPC | Yet to be finalized | Yet to be finalized | 150 | 0 | 150 | 2027-12-31 | 2027-12-31 | Hybrid
269 | 300 MW ISTS Connected Ground Mounted Solar PV Project / Waaree Renewable Technologies Limited | North Eastern Electric Power Corporation Limited (SPD) | Bikaner, Rajasthan | 300 | 0 | 300 | 2025-07-31 | 200 MW by 31-08-2026 100 MW by 31-12-2026 | Solar
270 |  | Juniper Green Beam Pvt LTd | Dev bhumi Dwarka, GJ (Bhogat) | 50 | 0 | 50 | 2025-05-01 | 2026-04-30 | wind
271 | NTPC, SECI | Juniper Green Beta Pvt LTd | Jodhpur, RJ | 300 | 0 | 300 | 2026-02-01 | 2026-04-30 | solar
272 |  | Juniper Green Cosmic Pvt LTd | Barju, Bikaner, RJ | 300 | 150 | 150 | 2026-02-28 | 2026-04-30 | solar
273 |  | Juniper Green Cosmic Pvt LTd | Bikaner, RJ | 100 | 0 | 100 | 2025-01-01 | 2026-04-30 | solar
274 | SJVN, SECI, NTPC | Juniper Green Energy Pvt LTd | Kalyanpur, Devbhumi Dwarka, GJ | 300 | 0 | 300 | 2026-06-30 | 2026-06-30 | wind
275 |  | Juniper Green Energy Pvt LTd | Barmer, RJ | 300 | 0 | 300 | 2027-03-01 | 2027-03-01 | wind
276 |  | Juniper Green Energy Pvt LTd | Mandsaur, MP | 300 | 0 | 300 | 2028-06-01 | 2028-06-01 | wind
277 |  | Juniper Green Energy Pvt LTd | Ramgarh | 300 | 0 | 300 | 2028-12-01 | 2028-12-01 | solar
278 |  | Juniper Green Energy Pvt LTd | Lakadiya, GJ | 300 | 0 | 300 | 2027-06-01 | 2027-06-01 | wind
279 |  | Juniper Green Energy Pvt LTd | Lakadiya, GJ | 150 | 0 | 150 | 2027-03-01 | 2027-03-01 | wind
280 |  | Juniper Green Energy Pvt LTd | Lakadiya, GJ | 200 | 0 | 200 | 2029-03-01 | 2029-03-01 | solar
281 |  | Juniper Green Energy Pvt LTd | Dev bhumi Dwarka, GJ | 100 | 0 | 100 | 2027-06-01 | 2027-06-01 | wind
282 |  | Juniper Green Energy Pvt LTd | Dev bhumi Dwarka, GJ | 200 | 0 | 200 | 2028-06-01 | 2028-06-01 | wind
283 |  | Juniper Green Energy Pvt LTd | Sheo, Barmer, RJ | 50 | 0 | 50 | 2027-12-01 | 2027-12-01 | solar
284 |  | Juniper Green Energy Pvt LTd | Solapur, MH | 350 | 0 | 350 | 2028-06-01 | 2028-06-01 | solar
285 |  | Juniper Green Energy Pvt LTd | Solapur, MH | 50 | 0 | 50 | 2028-06-01 | 2028-06-01 | solar
286 |  | Juniper Green Energy Pvt LTd | Navinal, GJ | 600 | 0 | 600 | 2028-06-01 | 2028-06-01 | solar
287 |  | Juniper Green Energy Pvt LTd | Mandsaur, MP | 50 | 0 | 50 | 2028-06-01 | 2028-06-01 | wind
288 |  | Juniper Green Energy Pvt LTd | Dev bhumi Dwarka, GJ | 300 | 0 | 300 | 2028-06-01 | 2028-06-01 | wind
289 |  | Juniper Green Energy Pvt LTd | Lakadiya-II , GJ | 150 | 0 | 150 | 2028-06-01 | 2028-06-01 | wind
290 |  | Juniper Green Energy Pvt LTd | Lakadiya-II , GJ | 150 | 0 | 150 | 2028-06-01 | 2028-06-01 | solar
291 |  | Juniper Green Energy Pvt LTd | Merta, RJ | 300 | 0 | 300 | 2027-12-01 | 2027-12-01 | solar
292 | NTPC | Juniper Green Energy Pvt LTd | Bikaner, RJ | 130 | 0 | 130 | 2030-03-01 | 2030-03-01 | solar
293 |  | Juniper Green Gem Pvt Ltd | Dhule, MH | 100 | 0 | 100 | 2028-06-01 | 2028-06-01 | solar
294 |  | Juniper Green Gem Pvt Ltd | Dhule, MH | 200 | 0 | 200 | 2028-06-01 | 2028-06-01 | solar
295 |  | Juniper Green India Six Pvt Ltd | Jodhpur, RJ | 300 | 0 | 300 | 2028-06-01 | 2028-06-01 | solar
296 |  | Juniper Green Kite Pvt LTd | Dev bhumi Dwarka, GJ | 70 | 0 | 70 | 2025-08-01 | 2026-03-31 | wind
297 |  | Juniper Green Kite Pvt LTd | rajkot, GJ | 90 | 0 | 90 | 2026-06-01 | 2026-06-01 | wind
298 | SJVN | Juniper Green Stellar Pvt LTd | Sheo, Barmer, RJ | 500 | 135 | 365 | 2026-06-01 | 2026-06-01 | hybrid
299 | SJVN | Juniper Green Stellar Pvt LTd | Sheo, Barmer, RJ | 300 | 0 | 300 | 2026-12-01 | 2026-12-01 | solar
300 |  | Juniper Nirjara Energy Pvt LTd | Bikaner, RJ | 100 | 50 | 50 | 2025-12-31 | 2026-03-31 | solar
301 | - | Amplus Everest Pvt. Ltd. | Dist. Cuddapah, Andhra Pradesh | 130 | 0 | 130 | 2026-12-31 | 2026-12-31 | Hybrid
302 | - | Amplus IIFA Solar Pvt. Ltd. | Dist. Cuddapah, Andhra Pradesh | 130 | 0 | 130 | 2026-12-31 | 2026-12-31 | Hybrid
303 | - | Amplus Sun Beat Pvt. Ltd. | Dist. Karur, Tamil Nadu | 80 | 0 | 80 | 2026-12-31 | 2026-12-31 | Wind
304 | - | Amplus Theta Energy Pvt. Ltd. | Dist. Karur, Tamil Nadu | 65 | 0 | 65 | 2026-12-31 | 2026-12-31 | Wind
305 | NTPC | BN Dispatchable-1 Pvt Ltd (Yanara Power) | Tehsil- Sheo, District - Barmer, State -Rajasthan | 110 | 0 | 110 | 2026-02-28 | 2027-04-10 | Hybrid
306 | NHPC | BN Hybrid Power-1 Pvt Ltd (Yanara Power) | Tehsil- Sheo, District - Barmer, State -Rajasthan | 120 | 0 | 120 | 2026-08-22 | 2027-07-29 | Hybrid
307 | MSEDCL | BN Peak Power-1 Pvt Ltd (Yanara Power) | District - Osmanabad, State - Maharastra | 89 | 0 | 89 | 2026-10-24 | 2026-10-24 | Hybrid
308 | NTPC | ACME Alpha Renewables Private Limited | Mandsaur, Madhya Pradesh Devbhumi Dwarka,Gujarat | 150 | 0 | 150 | Solar-31-03-2027 Wind - 14- 10-2026 | PPA Pending | Hybrid
309 | GUVNL | ACME Eco Clean Energy Pvt. Ltd | Surendranagar, Gujarat | 100 | 68 | 32 | 2025-10-17 | 12 MW - 15-02-2026 18 MW - 18-02-2026 12 MW - 15-03-2026 | Wind
310 | NHPC | ACME Hybrid Urja Private Limited | Bellary, Karnataka | 280 | 0 | 280 | 21-09-2027 (As per Final Grant) | 2027-01-23 | FDRE
311 | NTPC | ACME Marigold Urja Private Limited | Ananthapur, Andhra Pradesh. | 400 | 0 | 400 | 2027-10-18 | PPA Pending | Hybrid (FDRE)
312 | SJVN | ACME Omega Urja Private Limited | Tumkur, Karnataka | 300 | 0 | 300 | Grant Pending | PPA Pending | Solar
313 | SECI | ACME Platinum Urja Private Limited | Tumkur, Karnataka | 350 | 0 | 350 | 01-01-2027 (As per Final Grant) | 150 MW - 01-03-2027 200 MW - 30-06-2027 | Solar+BESS
314 | NHPC | Acme Renewtech Fifth Private Limited | Chittorgarh, Rajasthan | 250 | 0 | 250 | 2026-04-30 | 2027-06-18 | FDRE
315 | NTPC | ACME Renewtech Private Limited | Bikaner, Rajasthan Pachora, Madhya Pradesh | 300 | 0 | 300 | Solar-22-08-26 | 2026-09-21 | Hybrid
316 | SECI | ACME Renewtech Second Private Limited | Banashkatha, Gujarat Pachora, MP | 300 | 0 | 300 | Solar-30-04-2027 Wind - 14- 10-2026 | PPA Pending | Hybrid
317 | NHPC | Acme Renewtech Sixth Private Limited | Jaisalmer,Rajasth an Devbhumi Dwarka, Gujarat | 250 | 0 | 250 | 31-03-2027 (Solar) 14-10-2026 (Wind) | PPA Pending | FDRE
318 | Tata Power Distribution Company Limited | Acme Sigma Urja Private Limited | Chhitorgarh,Rajas than | 50 | 0 | 50 | 2027-10-16 | 2027-10-16 | Hybrid (FDRE)
319 | SJVN | Acme Solar Holdings Limited | Bikaner, Rajasthan Jaisalmer,Rajasth an | 450 | 0 | 450 | Grant Pending | PPA Pending | Assured Peak Power
320 | REMCL | Acme Solar Holdings Limited | Devbhumi Dwarka,Gujarat Banaskantha,Guja rat | 130 | 0 | 130 | PPA Pending | PPA Pending | Hybrid (RTC)
321 | SJVN | ACME Sun Power Private Limited | Jaisalmer,Rajasth an Bhadla, Rajasthan | 320 | 0 | 320 | 300 MW Solar - 31- 03-2027 240 MW Solar - 31- 03-2027 300 MW BESS - 31- 03-2027 | 2027-01-21 | FDRE
322 | SJVN | ACME Surya Power Private Limited | Jaisalmer,Rajasth an, Bikaner, Rajasthan | 250 | 0 | 250 | 250 MW Solar - 31- 03-2027 190 MW Solar - 31- 03-2027 250 MW BESS - 31- 03-2027 | 2027-01-21 | FDRE
323 | SECI | ACME Urja One Private Limited | Anantapuram, Andhra Pradesh Pachora, Madhya Pradesh | 380 | 0 | 380 | Solar-31-05-26 (As per Final Grant) Wind - 30- 04-2026 (As per In-Principle grant) | 2027-10-14 | Hybrid
324 | NHPC | ACME Venus Urja Private Limited | Barmer, Rajasthan | 400 | 0 | 400 | 2027-06-30 | 2027-01-23 | FDRE
325 | 50MW Hybrid Power Project | Amiya Wind Energy private Limited | BHUJ II, Gujarat | Connectivity approval awaited |  |  | 2027-12-31 | 2027-12-31 | Hybrid
326 | 100MW Wind Power Project | Dangri Wind Energy Private Limited | Ramgarh. Jaisalmer Rajasthan | 100 | 0 | 100 | 2030-03-31 | 2030-03-31 | Wind
327 | 100MW Wind Power Project | Dharvi kalan Wind Energy Private Limited | Ramgarh. Jaisalmer Rajasthan | 100 | 0 | 100 | 2030-03-31 | 2030-03-31 | Wind
328 | 100MW Wind Power Project | Ghanikhedi Wind Energy Private Limited | BHUJ II, Gujarat | Connectivity approval awaited |  |  | 2027-12-31 | 2027-12-31 | Wind
329 | Purvah Green Power Privarte Limited | Inox Green Energy Services Limited | ISTS - Bhuj Pool II, Gujarat | 300 | 0 | 300 | 2027-03-31 | 2026-12-31
330 | 500MW Project - Renewable Park | Inox Wind Energy Limited | STU - Dangri II, Rajasthan | 500 | 0 | 500 |  | 2026-12-31 | Renewable Park
331 | EPC | Inox Wind Energy Limited | STU - Sukhpur, Gujarat | 550 | 503 | 47 |  | 2026-12-31
332 | EPC | Inox Wind Energy Limited | STU - Golida, Gujarat | 120 | 100 | 20 |  | 2026-12-31
333 | EPC | Inox Wind Energy Limited | STU - Dangri II, Rajasthan | 500 | 0 | 500 |  | 2026-12-31
334 | NLC - 50MW wind capacity | INOX WIND LIMITED | ISTS - Bhuj pool I, Gujarat | 50 | 0 | 50 | 2025-06-30 | 2026-03-31 | Wind
335 | OYSTER GREEN HYBRID ONE PRIVATE LIMITED - 99MW wind capacity | INOX WIND LIMITED | ISTS - Bhuj pool I, Gujarat | 99 | 0 | 99 | 2025-06-30 | 2026-03-31 | Wind
336 | NTPC - 150MW wind capacity (Wind portion of SECI hybrid Tranche IV) | INOX WIND LIMITED | ISTS - Bhuj pool I, Gujarat | 150 | 50 | 100 | 2024-04-30 | 2026-03-31 | Hybrid
337 | Purvah Green Power Privarte Limited | INOX WIND LIMITED | ISTS - Bhuj pool I, Gujarat | 99 | 0 | 99 | 2025-06-30 | 2026-03-31
338 | NTPC | INOX WIND LIMITED | ISTS - Bhuj Pool II, Gujarat | 150 | 0 | 150 | 2024-10-22 | 2026-03-31
339 | EPC | Inox Wind Limited | STU - Kalawad, Gujarat | 150 | 0 | 150 |  | 2026-12-31
340 | 100MW Wind Power Project | Junachay Wind Energy Private Limited | Ramgarh. Jaisalmer Rajasthan | 100 | 0 | 100 | 2030-03-31 | 2030-03-31 | Wind
341 | 100MW Wind Power Project | Kadodiya Wind Energy Private Limited | Jamnagar, Gujarat | Connectivity approval awaited |  |  | 2027-12-31 | 2027-12-31 | Wind
342 | 50MW Wind Power Project | Lakhapar Wind Energy Private Limited | BHUJ II, Gujarat | Connectivity approval awaited |  |  | 2027-12-31 | 2027-12-31 | Wind
343 | 100MW Wind Power Project | Laxmansar Wind Energy Private Limited | BHUJ II, Gujarat | Connectivity approval awaited |  |  | 2027-12-31 | 2027-12-31 | Wind
344 | 99MW Wind Power Project | Pokhran Wind Energy Private Limited | Fategarh IV, Rajasthan | Connectivity approval awaited |  |  | 2027-12-31 | 2027-12-31 | Wind
345 | Purvah Green Power Privarte Limited | Resco Global Wind Services Private Limited | ISTS - Jam Nagar, Gujarat | 100 | 0 | 100 | 2027-03-30 | 2027-03-30
346 | Purvah Green Power Privarte Limited | Resco Global Wind Services Private Limited | ISTS - Jam Khambaliya, Gujarat | 500 | 0 | 500 | 2027-03-30 | 2027-03-30
347 | Purvah Green Power Privarte Limited | Resco Global Wind Services Private Limited | ISTS - Fategarh II, Rajasthan | 300 | 0 | 300 | 2027-03-30 | 2027-03-30
348 | Purvah Green Power Privarte Limited | Resco Global Wind Services Private Limited | ISTS - Pachoda, MP | 200 | 0 | 200 | 2026-09-30 | 2026-09-30
349 | EPC | Resco Global Wind Services Private Limited | STU - Akal, Rajasthan | 76 | 0 | 76 | Awaited | 2027-03-30
350 | EPC | Resco Global Wind Services Private Limited | STU - Lahori, MP | 240 | 0 | 240 | Awaited | 2027-03-30
351 | EPC | Shri Jai Ambe Energy Private Limited | STU - Kariyana, Gujarat | 50 | 44 | 6 |  | 2026-12-31
352 | 100MW Wind Power Project | Waft Energy Private Limited | Ladwan, Agar, Madhya Pradesh | 100 | 0 | 100 | 2027-03-31 | 2027-03-31 | Wind
353 | Kallam | Serentica Renewable India 5 Pvt Ltd. | Kallam, Maharashtra | 150 | 0 | 150 | 2025-10-05 | 2026-06-30 | Wind
354 | Lakadia | Serentica Renewable India Pvt Ltd. | Kutch, Gujarat | 960 | 0 | 960 | 2027-03-31 | 2027-03-31 | Hybrid
355 | 350 MW Wind project at Kallam, Maharashtra | Serentica Renewable India 4 Pvt Ltd. | Kallam, Maharashtra | 350 | 0 | 350 | 2025-10-05 | 200 MW- Sept'26 150 MW- Dec'26 | Wind
356 | 500 MW Hybrid Plant at Solapur | Serentica Renewable India Pvt Ltd. | Solapur, Maharashtra | 500 | 0 | 500 | 2025-03-31 | 150 MW- 31/12/202 6 (WIND) 150 MW- 31/03/202 7 (WIND) 100 MW- 31/06/202 7 (WIND) | Hybrid
357 | 300 MW Wind Project at Kallam | Serentica Renewable India Pvt Ltd. | Kallam, Maharashtra | 300 | 0 | 300 | 2025-10-05 | As per GNA effectivene ss | Wind
358 | C&I | Asnen Solar Private Limited | Mandsaur-Madhya Pradesh | 200 | 0 | 200 | 2027-05-31 | 2027-05-31 | Solar
359 | SECI 1200MW ISTS- connected Wind Solar Hybrid Power Projects (Tranche-VIII) | Asurari Renewables India Project Pvt Ltd | District, Karnataka (Wind) | 200 | 0 | 200 | 2028-03-31 | 2028-03-31 | Hybrid
360 | KUSUM Projects | Reliance New Eergy | Beed, Maharashtra | 150 | 0 | 150 | 2027-10-31 | 2027-10-31 | Solar
361 | C&I | Skadar Solar Private Limited | Solapur-Maharashtra | 200 | 0 | 200 | 2026-05-31 | 2026-05-31 | Solar
362 | CESC | AMP Energy Green Seventeen Pvt. Ltd. | Nandyala, State-Andhra Pradesh | 150 | 0 | 150 | 2026-03-31 | 31-03-2026 (In line with connectivit y operational ization date) | Hybrid
363 | SECI Hybrid-5 | AMPIN Energy Green Sixteen Pvt. Ltd. | District-Barmer, State-Rajasthan | 120 | 120 | 0 | 2026-06-30 | 30-06-2026 (In line with connectivit y operational ization date) | Hybrid
364 | SECI Hybrid-6 | AMPIN Energy Green Ten Pvt. Ltd. | Andhra Pradesh | 100 | 0 | 100 | 2026-10-27 | 2026-10-27 | Hybrid
365 | NTPC Hybrid-2 | AMPIN Energy Utility Five Pvt. Ltd. | District: Jalore, State: Rajasthan | 150 | 0 | 150 | 2027-12-31 | PPA Not Signed | Hybrid
366 | SECI Hybrid-8 | AMPIN Energy Utility Four Pvt. Ltd. | District : Bidar, Karnataka | 150 | 0 | 150 | 2027-12-31 | PPA Not Signed | Hybrid
367 | NTPC Hybrid-5 | AMPIN Energy Utility Three Pvt. Ltd. | District-Tumkur, State-Karnataka | 150 | 0 | 150 | 2027-12-31 | PPA Not Signed | Hybrid
368 | SJVN HB-2 | AMPIN Energy Utility Two Pvt. Ltd. | Village: Bhalki, Tehsil: Bhalki Taluk, District : Bidar, Karnataka | 150 | 0 | 150 | 2027-12-31 | PPA Not Signed | Hybrid
369 | M/s. Oyster Renewable Energy Private Limited. | Oyster Green Hybrid One private Limited. | Agar (MP) | 100 | 0 | 100 | 2026-02-14 | 2026-06-30 | Hybrid
370 | M/s. Oyster Renewable Energy Private Limited. | Oyster Green Hybrid One private Limited. | Agar (MP) | 81 | 53 | 18 | 2026-02-14 | 2026-06-30 | Hybrid
371 | M/s. Oyster Green Hybrid One private Limited. | Oyster Green Hybrid One private Limited. | Dayapar, Kutch (GJ) | 99 | 0 | 99 | 2026-10-31 | 2026-10-31 | Wind
372 | Serentica 432 MW Hybrid Plant at Ananthapur | NA | Anathapur, Andhra Pradesh | 432 | 0 | 432 | 2027-03-31 | 2027-03-31 | Hybrid
373 | Serentica 720 MW Hybrid Plant at Devangere | NA | Devangere, Karnataka | 720 | 0 | 720 | 2026-08-31 | 360 MW(solar): 30.06.2027 360MW(wi nd): 31.03.2028 | Hybrid
374 | Serentica 900 MW Wind Project at Gadag-II | NA | Dharawad & Koppal, Karnataka | 900 | 0 | 900 | 350 MW- 12/30/2025 550 MW- 17/01/2027 | 150MW: 31.01.2027 200MW: 31.12.2027 550 MW- 17.01.2027 | Wind
375 | Serentica 100 MW Wind Project at Bellary | NA | Bellary | 100 | 0 | 100 |  | 2027-06-30 | Wind
376 | Serentica 399.8 MW Hybrid Project at Koppal, Karnataka | SRIPL1 | Koppal, Karnataka | 399.8 | 386.7 | 13.1 | 2024-10-31 | 2026-06-30 | Hybrid
377 | Serentica 470 MW Hybrid Project at Gadag, Karnataka | SRIPL3 | Gadag, Karnataka | 470 | 340.915 | 129.085 | 2024-10-01 | 2026-06-30 | Hybrid
378 | 90 MW Wind Solar Hybrid Project | CGE RENEWABLES PRIVATE LIMITED | Kachchh, Gujarat | 90 | 0 | 90 | 2026-12-18 | 2026-12-31 | Hybrid
379 | 36 MW Wind Power Project | CONTINUUM POWER TRADING (TN) PVT. LTD. | Kachchh, Gujarat | 36 | 0 | 36 | 2026-11-19 | 2026-11-30 | Wind
380 | SECI Bhuj - II | Avaada GJGreen Pvt Ltd | Bhuj, Gujarat | 300 | 0 | 300 | 2026-03-31 | 2027-05-30 | Solar
381 | Manjusar GUVNL - III | Avaada GJSolar Private Limited | Manjusar, Gujarat | 200 | 0 | 200 | 2026-04-04 | 2026-10-04 | Solar
382 | GUVNL-400 MW- Solar-Ph. XXIV | Avaada GJSolar Private Limited | Gujarat | 400 | 0 | 400 | 2026-10-10 | 2027-04-10 | Solar
383 | GUVNL-250MW-Solar-Ph.26 | Avaada GJSustainable2 Pvt Ltd | Gujarat | 200 | 0 | 200 | 2027-08-24 | 2027-08-24 | Solar
384 | MSEDCL Hybrid - Ph. 3 | Avaada Green Sustainable Energy Private Limited | Maharashtra | 850 | 0 | 850 | 2026-11-25 | 2026-11-25 | Hybrid
385 | MSEDCL Hybrid - Ph. 4 | Avaada MHRenewable1 Private Limited | Maharashtra | 500 | 0 | 500 | 2026-11-21 | 2026-11-21 | Solar
386 | SJVN 1.2 GW FDRE II (Base) | Avaada RJBikaner Private Limited | Rajasthan | 590 | 0 | 590 | 2027-03-20 | 2027-03-20 | Solar
387 | NHPC-3GW-Solar-ISTS-1 | Avaada RJSustainable Pvt Ltd | Bikampur, Rajasthan | 300 | 0 | 300 | 2026-04-30 | 2030-03-31 | Solar
388 | NHPC-3GW-Solar-ISTS-1 | Avaada RJSustainable Pvt Ltd | Madhya Pradesh | 700 | 0 | 700 | 2026-04-30 | 2027-07-31 | Solar
389 | MSEDCL Shirdhane | Avaada SunEnergy Pvt. Ltd. | Shridhane, Maharshtra | 400 | 0 | 400 | 2026-03-31 | 2026-03-31 | Solar
390 | SJVN 1.2 GW FDRE II (Greenshoe) [200 MW PSPCL] | Avaada Sunurja Private Limited | Madhya Pradesh | 200 | 0 | 200 | 2028-03-09 | 2028-03-09 | Hybrid
391 | NTPC Solar BOO-9 | Avaada Surya Power Private Limited | Fatehgarh, Rajasthan | 300 | 0 | 300 | 2026-06-30 | 2027-06-30 | Solar
392 | MSKVY KUSUSM - 6 | Avaada Sustainable Urja Private Limited | PM-KUSUM Distributed, Maharashtra | 98 | 69 | 29 | 2027-03-31 | 2027-04-01 | Solar
393 | NHPC-88 MW-Hybrid- 1 | Avaada Wind Energy Private Limited | Bikaner, Rajasthan | 88 | 0 | 0 | 2027-12-10 | 2027-12-10 | Solar
394 | NHPC-88 MW-Hybrid-1 | Avaada Wind Energy Private Limited | Kallam, Dharashiv, Maharashtra | 29.3333 | 0 | 0 | 2027-12-10 | 2027-12-10 | Wind
395 | Pune MSKVY | MSKVY Eleventh Solar Private Limited | PM-KUSUM Distributed, Maharashtra | 225 | 140 | 85 | 2027-03-31 | 2027-04-01 | Solar
396 | Sangli MSKVY | MSKVY Fifth Solar Private Limited | PM-KUSUM Distributed, Maharashtra | 207 | 188.8 | 18.2 | 2027-03-31 | 2027-04-01 | Solar
397 | Yavatmal MSKVY | MSKVY First Kusum Private Limited | PM-KUSUM Distributed, Maharashtra | 225 | 188 | 37 | 2027-03-31 | 2027-04-01 | Solar
398 | Ahmednagar MSKVY | MSKVY Tenth Solar Private Limited | PM-KUSUM Distributed, Maharashtra | 234 | 126 | 108 | 2027-03-31 | 2027-04-01 | Solar
399 | Nashik MSKVY | MSKVY Twentieth Solar Private Limited | PM-KUSUM Distributed, Maharashtra | 207 | 90 | 117 | 2027-03-31 | 2027-04-01 | Solar
400 | Exchange | Iris Renewables Six Private Limited | Site:- Gadag State :- Karnataka | 100 | 0 | 100 | 2027-06-28 | 2027-06-28 | Wind
401 | Exchange | Rinnovabile Energy Private Limited | Site:- Gadag State :- Karnataka | 99 | 0 | 99 | 2026-12-31 | 2026-12-31 | Wind
402 | ArcelorMittal Nippon Steel India Limited, hybrid project | ArcelorMittal Nippon Steel India Limited | Lakadia PS, Gujarat | 250 | 0 | 0 | 2026-11-11 | 2026-11-11 | Hybrid
404 | NA | Proteus Energy Private Limited | Bikaner-III, Rajasthan | 217 | 0 | 217 | 2026-11-28 | 2026-12-28 | Solar
405 | NA | VEH Damen Power Private Limited | Agar Malwa, Madhya Pradesh | 76.8 | 0 | 76.8 | 2026-03-31 | 2026-06-30 | Wind
406 | NA | VEH Green Energy Private Limited | Koppal-II, Karnataka | 153.6 | 0 | 153.6 | 2025-12-31 | 2026-06-30 | Wind
407 | C&I | VEH Jayin Renewables Private Limited | Rajgarh, Madhya Pradesh | 196.8 | 0 | 196.8 | 2026-06-15 | 2026-06-30 | Hybrid
408 | NA | VEH Power Nirman Private Limited | Koppal-II, Karnataka | 76.8 | 0 | 76.8 | 2026-03-31 | 2026-06-30 | Wind
409 | NA | VEH Saur Urja Private Limited | Agar Malwa, Madhya Pradesh | 163.2 | 0 | 163.2 | 2025-06-30 | 2026-06-30 | Wind
410 | C&I | VEH Wind Energy Private Limited | Rajgarh, Madhya Pradesh | 75 | 0 | 75 | 2026-06-15 | 2026-06-30 | Wind
411 | SJVN | Green Pararie Enrgy Pvt Ltd | Solapur, Maharashtra | 60 | 0 | 60 | 2026-11-01 | 2026-11-01 | Hybrid
412 | NTPC | Green Prairie Energy III Pvt Ltd | Solapur, Maharashtra | 200 | 0 | 60 | 2027-03-01 | 2027-03-01 | Hybrid
413 | NTPC | Green Prairie Energy IV Pvt Ltd | Dhule, Maharashtra | 200 | 0 | 60 | 2027-04-01 | 2027-04-01 | Hybrid
414 | SJVN | Inaayu Renewables Pvt Ltd | Solapur, Maharashtra | 60 | 0 | 60 | 2026-10-01 | 2026-10-01 | Hybrid
415 | TPREL 330MW Valsang Solar Project | Tata Power Renewable Energy Limited | Solapur , Maharashtra | 288 | 0 | 288 | 2024-01-10 | 2026-04-01 | Solar
416 | 151.2 MW Wind SJVN FDRE Basis LOA | Tata Power Renewable Energy Limited | Pugalur Tamil Nadu | 151.2 | 0 | 151.2 |  | 2026-12-31 | Wind
417 | 93.6 MW Karur - SJVN FDRE Green Shoe | Tata Power Renewable Energy Limited | Karur, Tamil Nadu | 93.6 | 0 | 93.6 |  | 2026-05-02 | Wind
418 | 151 MW SJVN Wind Palayam Green Shoe | Tata Power Renewable Energy Limited | Pugalur Tamil Nadu | 151.2 | 0 | 151.2 |  | 2027-01-31 | Wind
419 | 180 MW Parali Wind NTPC FDRE | Tata Power Renewable Energy Limited | Parli, Maharashtra | 180 | 0 | 180 |  | 2027-04-11 | Wind
420 | 10.8 MW Kallam Wind | Tata Power Renewable Energy Limited | Kallam, Maharashtra | 10.8 | 0 | 10.8 |  | 2026-04-30 | Wind
421 | 400 MW Kurnool 4 (Solar) | Tata Power Renewable Energy Limited | Kurnool, AP | 400 | 0 | 400 |  | 2027-03-31 | Solar
422 | 600 MW Solar | Tata Power Renewable Energy Limited | Ramgarh, Rajasthan | 600 | 0 | 600 |  | 2030-03-31 | Solar
423 | 82.5 MW NTPC FDRE Wind | Tata Power Renewable Energy Limited | Karur, Tamil Nadu | 82.5 | 0 | 82.5 |  | 2026-12-31 | Wind
424 | 220 MW Parali Wind | Tata Power Renewable Energy Limited | Parli, Maharashtra | 220 | 0 | 220 |  | 2027-03-01 | Wind
425 | 300MW Kurnool 4 Solar | Tata Power Renewable Energy Limited | Kurnool, AP | 300 | 0 | 300 |  | 2028-03-31 | Solar
426 | 400MW Ananthpur 2 | Tata Power Renewable Energy Limited | Ananthapuram, AP | 400 | 0 | 400 |  | 2028-03-31 | Wind
427 | 300MW Ramgarh Wind | Tata Power Renewable Energy Limited | Ramgarh, Rajasthan | 300 | 0 | 300 |  | 2030-03-31 | Wind
428 | 300 MW Bikaner 6 Solar | Tata Power Renewable Energy Limited | Bikaner, Rajasthan | 300 | 0 | 300 |  | 2031-12-31 | Solar
429 | TPREL 112MW Koppal Wind Project | Tata Power Renewable Energy Ltd. | Koppal, Karnataka | 288 | 0 | 288 | 2024-10-01 | 2026-03-31 | Wind
430 | TPREL 300 MW Koppal Solar Project | Tata Power Renewable Energy Ltd. | Koppal , karnataka | 300 | 0 | 300 | 2025-12-27 | 2027-03-31 | Solar
431 | TPREL 400 MW Koppal Solar Project | Tata Power Renewable Energy Ltd. | Koppal , karnataka | 400 | 0 | 400 | 2027-01-17 | 2027-01-17 | Solar
432 | TPREL 170 MW Koppal Solar Project | Tata Power Renewable Energy Ltd. | Koppal , karnataka | 170 | 0 | 170 | 2025-01-02 | 2026-12-31 | Solar
433 | TPREL 202 .5 MW FDRE Koppal solar project | Tata Power Renewable Energy Ltd. | Koppal , karnataka | 235 | 0 | 235 | 2024-10-01 | 2026-11-30 | Solar
434 | TPREL 260MW FDRE GS Koppal Solar Project | Tata Power Renewable Energy Ltd. | Koppal , karnataka | 225 | 0 | 225 | 2024-10-31 | Connectivit y no. 220000039 0 revoked | Wind
435 | TPREL 288 MW Mudhol Wind Project | Tata Power Renewable Energy Ltd. | Bagalkot, Karnataka | 288 | 0 | 288 | 2025-12-31 | 2026-06-30 | Wind
436 | TPREL 340 MW Gadag Wind Project | Tata Power Renewable Energy Ltd. | Gadag, Karnataka | 340 | 0 | 340 | 2026-01-03 | 2026-09-30 | Wind
437 | TPREL 101 MW Kallam Wind Project | Tata Power Renewable Energy Ltd. | Osmanabad, Maharashtra | 101 | 0 | 101 | 2024-01-10 | 2026-04-30 | Wind
438 | TPREL 101 MW FDRE Kallam Wind Project | TATA POWER RENEWABLE ENERGY Ltd. | Osmanabad, Maharashtra | 101 | 0 | 101 | 2026-03-31 | Connectivit y revoked, case pending with CERC for restoration | Wind
439 | TPREL 50.4MW FDRE GS Bijapur Wind Project | TATA POWER RENEWABLE ENERGY Ltd. | Bijapur, | 50.4 | 0 | 50.4 | 2026-01-02 | 2027-04-01 | Wind
440 | TPREL 252MW Bijapur Wind Project | TATA POWER RENEWABLE ENERGY Ltd. | Bijapur, | 252 | 0 | 252 | 2027-01-17 | 2027-04-30 | Wind
441 | TPREL 100.8 MW FDRE GS Kallam Wind Project | TATA POWER RENEWABLE ENERGY Ltd. | Osmanabad , Maharashtra | 100.8 | 0 | 100.8 | 2026-01-03 | 2026-05-02 | Wind
442 | 101 MW Kallam Wind - Tata Steel | Tata Power Renewable Energy Ltd. | Osmanabad, Maharashtra | 101 | 0 | 101 | 2024-01-10 | 2026-04-30 | Wind
443 | TP Saurya Limited 300MW Bikaner3 | TP SAURYA LIMITED | Ajmer , Rajasthan | 300 | 0 | 300 | 2024-10-01 | 2026-05-03 | Solar
444 | 300 MW Solar - SECI Stage 2 | TP Saurya Limited | Koppal, Karnataka | 300 | 192 | 108 |  | 2026-02-24 | Solar
445 | TP Saurya Limited 200 MW Gadag Wind Project | TP Saurya Ltd. | Gadag, Karnataka | 200 | 0 | 200 | 2024-10-31 | 2026-08-31 | Wind
446 | NHPC | Energizent Power Pvt Ltd | Fatehgarh, Rajasthan | 205 | 0 | 205 | 24 months from PPA | 24 months from PPA | Solar
447 | NTPC | TEQ Green Power IX PrivateLimited | Barmer, Rajasthan | 208.5 | 0 | 208.5 |  | 2026-12-31 | Hybrid
448 | NTPC | TEQ Green Power IX PrivateLimited | Bellary, Karnataka | 83.5 | 0 | 83.5 |  | 2027-12-31 | Hybrid
449 | GUVNL | Teq Green Power Private Limited | Dholera, Gujarat | 200 | 0 | 200 |  | 2026-12-31 | Dholera Solar Park
450 | SECI | TEQ Green Power XI Pvt Ltd | Ahmednagar, Maharashtra | 200 | 0 | 200 | 2025-12-31 | 2026-03-31 | Wind
451 | REMCL | TEQ Green Power XIII Pvt Ltd | Kachchh, Gujarat | 120 | 0 | 120 | 2026-11-26 | 2027-06-30 | Wind
452 | REMCL | TEQ Green Power XIII Pvt Ltd | Bijapur, Karnataka | 120 | 0 | 120 | 2026-11-26 | 2027-06-30 | Wind
453 | REMCL | TEQ Green Power XIII Pvt Ltd | Barmer, Rajashtan | 120 | 0 | 120 |  | 2026-12-31 | Solar
454 | SJVN | TEQ Green Power XVI Pvt Ltd | Bijapur, Karnataka | 175 | 0 | 175 | 2027-01-15 | 2027-01-15 | Wind
455 | SJVN | TEQ Green Power XVI Pvt Ltd | Bijapur, Karnataka | 125 | 0 | 125 | 2027-01-15 | 2027-01-15 | Wind
456 | SJVN | TEQ Green Power XVI Pvt Ltd | Kachchh, Gujarat | 76 | 0 | 76 | 2027-12-31 | 2027-12-31 | Wind
457 | SJVN | TEQ Green Power XVI Pvt Ltd | Kachchh, Gujarat | 76 | 0 | 76 | 2027-12-31 | 2027-12-31 | Wind
458 | SJVN | TEQ Green Power XVI Pvt Ltd | Barmer, Rajashtan | 50 | 0 | 50 |  | 2026-12-31 | Solar
459 | SJVN | TEQ Green Power XVI Pvt Ltd | Bijapur, Karnataka | 70 | 0 | 70 |  | 2026-12-31 | Solar
460 | NTPC | TEQ Green Power XVII Pvt Ltd | Kachchh, Gujarat | 300 | 0 | 300 | 2026-08-14 | 2026-08-14 | Hybrid
461 | SJVN | TEQ Green Power XVIII Pvt Ltd | Anantapur, Andhra Pradesh | 200 | 0 | 200 | 2027-12-31 | 2027-12-31 | Wind
462 | 100MW Wind Project | EG Arka Solar Private Limited | Pavagada, Tumkur, KN | 100 | 0 | 0 | expected by Jun-28 | expected by Jun-28 | Wind
463 | 100MW Wind Project | EG Electricia Energy Private Limited | Krishnagiri, Kurnool, AP | 100 | 0 | 0 | expected by Jun-28 | expected by Jun-28 | Wind
464 | 100MW Wind Project | EG Energia Supply Private Limited | Krishnagiri, Kurnool, AP | 100 | 0 | 0 | expected by Jun-28 | expected by Jun-28 | Wind
465 | 300MW Solar Project | EG Mega Urja Private Limited | Barmer, Rajasthan | 300 | 0 | 300 | 2026-12-30 | Expected by Dec-2026 | Solar
466 | 100MW Wind Project | EG Pavan Surya Power Private Limited | Kalyanpur, Devbhumi Dwarka, GJ | 100 | 0 | 0 | 2028-11-30 | 2028-11-30 | Wind
467 | 300MW Solar Project | EG Saur Urja Private Limited | Fatehgarh, Rajasthan | 300 | 0 | 300 | 2026-10-15 | Expected by Oct-2026 | Solar
468 | 100MW Wind Project | EG Solaire Power Private Limited | Khambaliya, Devbhumi Dwarka, GJ | 100 | 0 | 0 | 2028-11-30 | 2028-11-30 | Wind
469 | 100MW Wind Project | EG Solar Power Ventures Private Limited | Pavagada, Tumkur, KN | 100 | 0 | 0 | expected by Jun-28 | expected by Jun-28 | Wind
470 | 100MW Wind Project | EG Solwin Renewable Pvt. Ltd | Narasalagi, Kanakal, Bijapur Kn | 100 | 0 | 100 | 2027-01-16 | 2027-01-16 | Wind
471 | 100MW Wind Project | EG Sun Energy Private Limited | Pavagada, Tumkur, KN | 100 | 0 | 0 | expected by Jun-28 | expected by Jun-28 | Wind
472 | 100MW Wind Project | Enfinity Global Clean Energy Private Limited | Kalyanpur, Devbhumi Dwarka, GJ | 100 | 0 | 0 | 2028-11-30 | 2028-11-30 | Wind
473 | 100MW Wind Project | Enfinity Global Haritha Udwal Pvt. Ltd. | Sankanal And Hanchinal, Bijapur, KN | 100 | 0 | 0 | expected by Jun-28 | expected by Jun-28 | Wind
474 | 100MW Wind Project | Enfinity Global Sunsource Private Limited | Krishnagiri, Kurnool, AP | 100 | 0 | 0 | expected by Jun-28 | expected by Jun-28 | Wind
475 | 300MW Solar Project | Enfinity Global Surya Kiran Private Limited | Barmer, Rajasthan | 300 | 0 | 300 | 2026-12-30 | Expected by Dec-2026 | Solar
476 | 200MW Hybrid Project | Tepsol Green Energy Private Limited | Bijapur, Karnataka | 200 | 0 | 200 | expected by 16-01- 2027 | expected by 16-01- 2027 | Hybrid
477 | 300MW Solar Project | Tepsol Sun Sparkle Private Limited | Bhadla, Rajasthan | 300 | 0 | 300 | 2026-02-28 | expected by Sep-2026 | Solar
478 | Solar Power Project | Frugal Energy Private Limited | Jodhpur, Rajasthan | 300 | 0 | 300 | 2026-08-30 | 2026-08-30 | Solar
479 | Solar Power Project | Helia Energy Park Private Limited | Barmer, Rajasthan | 300 | 0 | 300 | 2026-08-21 | 2026-08-21 | Solar
480 | Solar Power Project | Radiant Star Solar Park Private Limited | Barmer, Rajasthan | 300 | 0 | 300 | 2026-10-15 | 2026-10-15 | Solar
481 | Kasaragod Solar Park Phase II | (Renewable Power Corporation of Kerala Limited – RPCKL – a JV of SECI & KSEB | Kasargod, Kerala | 105 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
482 | 1200 MW ISTS- Connected Wind-Solar Hybrid Power Projects (Tranche-III) | ABC Renewable Energy Private Limited | Nuthimadugu, Anantapur Dt. A.P and Chodiya Village, Jaisalmer, Rajasthan | 150 | 0 | 150 | 2027-12-31 | 2027-12-31 | Hybrid
483 | ABU RENEWABLES INDIA PRIVATE LIMITED (340 MW Solar Project) | ABU RENEWABLES INDIA PRIVATE LIMITED | Bikaner, Rajasthan | 340 | 0 | 340 | 2026-03-31 | 2026-03-31 | Solar
484 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Five A Limited |  | 250 | 0 | 250 | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | Solar
485 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Five A Limited |  | 250 | 0 | 250 | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | Solar
486 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Five B Limited |  | 250 | 0 | 250 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
487 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Five C Limited |  | 250 | 200 | 50 | 2025-10-01 | 2026-06-30 | Solar
488 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Five C Limited |  | 250 | 150 | 100 | 2026-11-05 | 2026-11-05 | Solar
489 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Five Limited |  | 250 | 0 | 250 | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | Solar
490 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Five Limited |  | 250 | 0 | 250 | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | Solar
491 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Four A Limited |  | 250 | 0 | 250 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
492 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Four A Limited |  | 250 | 0 | 250 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
493 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Four B Limited |  | 250 | 0 | 250 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
494 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Four B Limited |  | 250 | 0 | 250 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
495 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Four Limited |  | 250 | 0 | 250 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
496 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Four Limited |  | 250 | 0 | 250 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
497 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Seven A Limited |  | 167 | 0 | 167 | 2026-11-05 | 2026-11-05 | Solar
498 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Seven A Limited |  | 250 | 0 | 250 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
499 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six A Limited |  | 250 | 0 | 250 | 60 dys subsequent to the operational ization of LTA/ Connectivit y | 60 dys subsequent to the operational ization of LTA/ Connectivit y | Solar
500 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six A Limited |  | 250 | 138 | 62 | 60 dys subsequent to the operational ization of | 60 dys subsequent to the operational ization of | Solar
[7 empty] | LTA/ Connectivit y | LTA/ Connectivit y
501 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six A Limited |  | 234 | 0 | 234 | 56 days subsequent to the actual date of operational ization of Connectivit y under the GNA | 56 days subsequent to the actual date of operational ization of Connectivit y under the GNA | Solar
502 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six A Limited |  | 333 | 158 | 175 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
503 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six A Limited |  | 200 | 100 | 50 | 15 days subsequent to LTA Operational ization | 15 days subsequent to LTA Operationa lization | Solar
504 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six B Limited |  | 250 | 0 | 250 | 2026-11-05 | 2026-11-05 | Solar
505 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six B Limited |  | 67 | 0 | 67 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
506 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six B Limited |  | 500 | 0 | 500 | “actual commissio ning date of the Bay allocated to SPD at RVPN's 400kV Bhadla substation + 30 days” or "actual commissio ning date of the full project capacity”, whichever is earlier. | “actual commissio ning date of the Bay allocated to SPD at RVPN's 400kV Bhadla substation + 30 days” or "actual commissio ning date of the full project capacity”, whichever is earlier. | Solar
507 | Manufacturing plant linked Solar Project scheme | Adani Green Energy Twenty Six B Limited |  | 100 | 0 | 100 | 2027-06-30 | 2027-06-30 | Solar
508 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Five Limited |  | 83 | 0 | 83 | 2026-10-01 | 2026-10-01 | Solar
509 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Five Limited |  | 100 | 0 | 100 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
510 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Five Limited |  | 150 | 0 | 150 | 15 days subsequent to the operational ization of | 15 days subsequent to the operational ization of | Solar
[7 empty] | LTA/connec tivity. | LTA/connec tivity.
511 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Five Limited |  | 134 | 0 | 134 | 2026-10-01 | 2026-10-01 | Solar
512 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Seven Limited |  | 100 | 0 | 100 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
513 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Seven Limited |  | 250 | 0 | 250 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
514 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Seven Limited |  | 150 | 0 | 150 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
515 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Seven Limited |  | 100 | 0 | 100 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
516 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Seven Limited |  | 200 | 0 | 200 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
517 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Seven Limited |  | 99 | 0 | 99 | 15 days subsequent to the operational ization of LTA/connec tivity. | 15 days subsequent to the operational ization of LTA/connec tivity. | Solar
518 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Seven Limited |  | 150 | 0 | 150 | 2026-10-01 | 2026-10-01 | Solar
519 | Manufacturing plant linked Solar Project scheme | Adani Renewable Energy Fifty Six Limited |  | 250 | 0 | 250 | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | 15 days subsequent to the actual date of operational ization of connectivit y under the GNA | Solar
520 | 1200 MW ISTS- connected Wind Power Projects (Tranche-XI) | Adani Renewable Energy Holding Fifteen Limited | Gadag, Karnataka | 450 | 0 | 450 | 2026-01-23 | 2026-12-31 | Wind
521 | Fatehgarh Phase -1B Solar Park | Adani Renewable Energy Park Rajasthan Ltd. – AREPRL – a JV of State Govt. & Adani Renewable Energy Park Ltd | Fatehgarh, Jaisalmer, Rajasthan | 1500 | 1234 | 266 | 2025-02-02 | 2026-12-31 | Solar
522 | 500 MW ISTS- connected Wind Power Projects (Tranche-XVII) | Adyant Enersol private limited | Dhule, Maharashtra | 380 | 0 | 380 | 2027-12-31 | 2027-12-31 | Wind
523 | 1200 MW ISTS- connected Wind Power Projects (Tranche-XI) | Anupavan Renewables pvt Ltd | Osmanabad, Maharashtra | 120 | 0 | 120 | 2025-12-31 | 2026-12-31 | Wind
524 | Kadapa Ultra Mega Solar Park (APSPCL - a JV of NREDCAP, APGENCO & SECI.) | APSPCL - a JV of NREDCAP, APGENCO & SECI | Mylavaram Mandal, Andhra Pradesh | 1000 | 250 | 750 | 2026-12-31 | 2026-12-31 | Solar
525 | CPSU Scheme (Tranche-I, 2000 MW) | Assam power Distribution Company Limited |  | 100 | 0 | 100 | 2027-12-31 | 2027-12-31 | Solar
526 | 320 MW Solar-Wind Hybrid Project | Cannice Renewables Energy Pvt Ltd | Barmer | 320 | 0 | 320 | 2026-02-28 | 2026-06-30 | Hybrid
527 | 2000 MW ISTS Tranche-XI | Eden Renewable Cadet Private Limited |  | 300 | 0 | 300 | 2025-06-30 | PPA yet to be signed | Solar
528 | 1200 MW ISTS- connected Wind Power Projects (Tranche-X) | Evergreen Power Mauritius Pvt Ltd | Osmanabad, Maharashtra | 150 | 0 | 150 | 2025-07-26 | 2026-12-31 | Wind
529 | 1070 MW Grid- Connected Solar PV Power Projects in Rajasthan (Tranche-III) | Green Infra Renewable Projects Limited |  | 81 | 5 | 76 | 2027-12-31 | 2027-12-31 | Solar
530 | 1200MW ISTS- connected Solar Wind Hybrid Power Projects (Tranche-VII) | Green Infra Wind Energy Limited | Rajasthan Gujarat | 150 | 0 | 150 | 2026-12-16 | 2026-12-16 | Hybrid
531 | 1200 MW ISTS- connected Wind Power Projects (Tranche-XI) | Green lnfra Wind Energy Limited | Koppal, Karnataka | 450 | 0 | 450 | 2025-07-26 | 2026-12-31 | Wind
| Jalaun Solar Park | Bundelkhand Saur Urja Limited – BSUL – a JV of NHPC & UPNEDA |  | 1200 | 0 | 0 | 2025-08-31 | 2026-12-31
532 | GSECL RE Park | GSECL | Khavda, Bhuj, Gujarat | 3325 | 0 | 3325 | 2025-03-31 | 2026-12-31 | Solar
533 | 2000 MW ISTS Tranche-XI | Jakson Limited |  | 50 | 0 | 50 | 2026-04-24 | 2026-04-24 | Solar
534 | Jindal Renewables - Wind Project - C&I | Jindal Green Wind 1 Private Limited | Mandsaur, MP | 350 | 0 | 350 |  |  | Wind
535 | 2500 MW ISTS- connected Blended Wind Power Projects (Tranche-IX) | JSW Future Energy Ltd (formerly JSW Solar Ltd) |  | 150 | 0 | 150 | 2027-12-31 | 2027-12-31 | Wind
536 | 1200 MW ISTS Tranvhe-XV | JSW Neo Energy Limited |  | 150 | 0 | 150 | 2027-02-04 | 2027-04-02 | Solar
537 | 1200 MW ISTS- connected Wind Power Projects (Tranche-XII) | JSW Neo Energy Ltd | Osmanabad, Maharashtra | 200 | 0 | 200 | 2025-12-27 | 2026-12-31 | Wind
538 | 1350 MW ISTS- connected Wind Power Projects (Tranche-XVI) | JSW Neo Energy Ltd | Kutch, Gujarat | 175 | 0 | 0 | 2027-03-31 | 2027-03-31 | Wind
539 | 1350 MW ISTS- connected Wind Power Projects (Tranche-XVI) | JSW Neo Energy Ltd | Davangere, Karnataka | 50 | 0 | 50 | 2027-03-01 | 2027-03-01 | Wind
540 | 1350 MW ISTS- connected Wind Power Projects (Tranche-XVI) | - | Davangere, Karnataka | 1175 | 50 | 1125 | 2025-03-31 | 2026-06-30 | Wind
541 | 1500 MW ISTS Tranche-XIII | JSW Renew Energy Eleven Limited |  | 300 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
542 | 1200MW ISTS- connected Solar Wind Hybrid Power Projects (Tranche-VII) | Juniper Green Energy Private Limited | Rajasthan Gujarat | 250 | 0 | 250 |  |  | Hybrid
543 | Engie Energy India Private Limited (formyl known as Solairedirect Energy India Private Limited | Khaba Renewable Energy Private Limited | Khodal, Bariyada, Mati ka Gol, Tehsil - Sheo, Barmer Distt. RJ | 250 | 0 | 0 | 2026-04-01 | 2026-04-01 | Solar
544 | Engie Energy India Private Limited (formyl known as Solairedirect Energy India Private Limited | Litsolaire Energy Private Limited | Village - Bhanipura, Tehsil - Pugal, Distt. - Bikaner | 100 | 0 | 0 | 2026-07-01 | 2026-07-01 | Solar
545 | Engie Energy India Private Limited (formyl known as Solairedirect Energy India Private Limited | Luceo Solar Private Limited | Village – Goonga, Tehsil – Sheo, Distt. - Barmer, RJ | 300 | 0 | 0 | 2025-10-01 | 2026-04-01 | Solar
546 | Dhar Solar Park | M/s Amar Infrastructure Limited | Dhar, Madhya Pradesh | 200 | 0 | 200 | 2025-08-31 | 2026-12-31 | Solar
547 | Battery Energy Storage system Project of 125 MW/500 MWh-ESS-3 | M/s JSW Renew Energy Thirty Eight Limited | Mylatti Kerala | 100 | 0 | 100 |  |  | Hybrid
548 | Patoda Solar Park | M/s Paramount Solar Pvt Ltd | Maharashtra | 250 | 0 | 250 | 2027-12-31 | 2027-12-31 | solar
549 | Dondaicha Solar Park | Maharashtra State Electricity Generating Co. Ltd. - MAHAGENCO | Methi & Vikharan, Dhule, Maharashtra | 250 | 0 | 250 | 2027-12-31 | 2027-12-31 | Solar
550 | 2000 MW ISTS Tranche-XI | MRS Green Energy Private Limited |  | 700 | 0 | 700 | 2026-10-18 | 2026-10-18 | Solar
551 | 1200MW ISTS- connected Solar Wind Hybrid Power Projects (Tranche-IV) | NLC India Limited | Tamil Nadu, Rajasthan | 150 | 0 | 150 | 2026-02-24 | 2026-12-31 | Hybrid
552 | 1200 MW ISTS Tranvhe-XV | Pace Digitek Private Limited |  | 250 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
553 | 1070 MW Grid- Connected Solar PV Power Projects in Rajasthan (Tranche-III) | Pavni (Raj) Solar Pvt Ltd (erstwhile: AEW India North One Private Limited) |  | 30 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
554 | 1200 MW ISTS Tranche-X | Project Eight Renewable Power Private Limited |  | 300 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
555 | 1200 MW ISTS Tranche-X | Project Eight Renewable Power Private Limited |  | 300 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
556 | Pugal Solar Park Ph-I | Rajasthan Solar Park Development Company Ltd. RSDCL- a subsidiary of RRECL | Pugal , Rajasthan | 2000 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
557 | Pugal Solar Park PhII | Rajasthan Solar Park Development Company Ltd. RSDCL- a subsidiary of RRECL | Pugal , Rajasthan | 1500 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
558 | Pugal Solar Park PhIII | Rajasthan Solar Park Development Company Ltd. RSDCL- a subsidiary of RRECL | Pugal , Rajasthan | 450 | 0 | 0 | 2025-03-31 | 2027-12-31 | Solar
559 | 2000 MW ISTS- Connected Solar PV Power Projects with 1000MW/4000 MWh Energy Storage Systems (ESS) (ISTS-XVII) | Reliance NU Suntech Private Limited |  | 400 | 102 | 298 | 2027-12-31 | 2027-12-31 | Solar
560 | SECI | ReNew Ushma Energy Private Limited |  | 300 | 0 | 300 | 2027-01-23 | 2027-01-23 | Solar
561 | Neemuch Solar Park | Rewa Ultra Mega Solar Limited RUMSL- a JV of MPUVN and SECI | Neemuch, Madhya Pradesh | 500 | 330 | 170 | 2027-12-31 | 2027-12-31 | Solar
562 | Nokh Solar Park | RSDCL | Nokh, Rajasthan | 925 | 827 | 78 | 2027-12-31 | 2027-12-31 | Solar
563 | Shajapur Solar Park | RUMSL | Shajapur, Madhya Pradesh | 450 | 105 | 345 | 2026-12-31 | 2026-12-31 | Solar
564 | 1500 MW ISTS Tranche-XIV | SAEL Industries Limited |  | 100 | 0 | 100 | 2026-10-27 | 2026-10-27 | Solar
565 | 1500 MW ISTS Tranche-XIV | SAEL Industries Limited |  | 500 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
566 | 500 MW ISTS- Connected Solar PV Power Projects (ISTS-XVI) | SAEL Industries Limited |  | 930 | 0 | 930 | 2027-04-18 | 2027-04-18 | Solar
567 | 2000 MW ISTS Tranche-XI | SAEL SOLAR MHP1 Pvt. Ltd. |  | 50 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
568 | SECI Floating Solar Park (SECI) | SECI | Getalsud Dam, Jharkhand | 100 | 0 | 100 | 2027-12-31 | 2027-12-31 | Solar
569 | Ramagiri Solar Park | SECI | Ramagiri, Sri Sathyasai , Andhra Pradesh | 300 | 0 | 300 | 2025-09-30 | 2026-11-30 | Solar
570 | 2000 MW ISTS- Connected Solar PV Power Projects with 1000MW/4000 MWh Energy Storage Systems (ESS) (ISTS-XVII) | Sembcorp Green Infra Private Limited |  | 200 | 0 | 200 | 2027-12-31 | 2027-12-31 | Solar
571 | 1200 MW ISTS Tranche-X | SolarOne Enegry Private Limited |  | 300 | 0 | 300 | 2025-06-30 | In line with clause 20.1 of RfS, SPD refused to sign PPA after timeline of PPA signing (90 days from LoA issuance) lapsed. Success charges returned and LoA annulled. | Solar
572 | 1200 MW ISTS Tranche-X | SolarOne Enegry Private Limited |  | 300 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
573 | 100 MW Solar Project | Sourya Manthan Renewable Energy Pvt Ltd | Bikaner | 100 | 0 | 100 | 2026-02-28 | 2026-06-30 | Solar
574 | 1500 MW ISTS Tranche-XIII | Sunsure Solarpark Fourteen Pvt. Ltd. |  | 300 | 0 | 0 | 2027-12-31 | 2027-12-31 | Solar
575 | SECI Solar | Tejorupa Renewables India Project Pvt Ltd | Barmer, Rajasthan | 250 | 0 | 0 | 2026-04-01 | 2026-04-01 | Solar
576 | SECI 1500MW ISTS- connected Solar Power Projects (Tranche-XIII) | Tejorupa Renewables India Project Pvt Ltd | Vill - Balai Kesharpura, Tehsil - Sheo, Dis-Barmer, State - Rajasthan | 300 | 0 | 300 |  |  | Solar
577 | CPSU Scheme (Tranche-II, 1500 MW) | The Singareni Collieries Company Limited |  | 333 | 0 | 333 | 2027-12-31 | 2027-12-31 | Solar
578 | 1200 MW ISTS- connected Wind Power Projects (Tranche-XII) | Torrent power Ltd | Bagalkot, Karnataka | 100 | 0 | 100 | 2027-03-31 | 2027-03-31 | Wind
579 | 1350 MW ISTS- connected Wind Power Projects (Tranche-XVI) | Torrent Power Ltd | Kuknoor, Karnataka | 150 | 0 | 150 | 2027-03-31 | 2027-03-31 | Wind
580 | 1200MW ISTS- connected Solar Wind Hybrid Power Projects (Tranche-V) | TP Saurya Limited | Karnataka | 150 | 0 | 150 | 2027-09-01 | 2027-01-09 | Hybrid
581 | Radiant Star Solar Park Pvt Ltd | Radiant Star Solar Park Private Limited | Fatehgarh, Rajasthan | 200MW | 0 | 200 | 2027-03-31 | 2027-03-31 | Solar
582 | Radiant Star Solar Park Pvt Ltd | Radiant Star Solar Park Private Limited | Fatehgarh, Rajasthan | 100MW | 0 | 100 | 2027-03-31 | 2027-03-31 | Solar
|  |  | Total | 165442.0333 | 13739.415 | 138320.685
This Report is published by Renewable Project Monitoring (RPM) Division Central Electricity Authority, New Delhi
In case of any query/update/discrepancy of information, Please contact at: 011-26732320, 2373 ce-rpmcea@cea.nic.in/cerpmcea@gmail.com